3 yr STEM Agenda Improvement Plan 2013-16

| Priority – To raise the profile of STEM agenda in CEC schools to further improve positive destination outcomes for young people | Overall Responsibility | QIs |
| --- | --- | --- |

| Outcome |  |  |  |  |
| --- | --- | --- | --- | --- |
| Impact |  |  |  |  |
| Tasks | By Whom | Resources | Timescale | Progress/evaluation of task |
| Consult with Economic development team, QIT team, CLs Science, Maths, Technologies to produce a draft position paper for schools which reflects national and local STEM priorities Look into feasibility of a STEM DO to lead priorities identified in position paper | Jill Pringle Alison Kidd | CL Science meeting on 29th August QIO Time | September 2013 August 2013 |  |
| Develop, Implement and Evaluate a pilot program for delivering CREST awards for all S1 learners at Forrester HS with a view to extending the program to other interested schools in 2014/15. Focus on sustainability. | Jill Pringle Alison Kidd Nick Langan | STEM ambassadors Mike Jeffrey – Edinburgh College Frank McKeever Pro Science | December 2013 |  |
| Engage CLs in the development and start up of STEM clubs in all CEC secondary schools which may be developed as a focus for cluster transition in the next stage of CEC STEM strategy. Identification of one STEM lead per school for future communications (all educational establishments) | Jill Pringle Alison Kidd CLs of Science, Maths and Technologies | Global Science CLs Pro Science QIO Time ‘STEM lead’ in school time Young engineers and Science Clubs (comes with funding) | From August 2013 – June 2014. August 2013 |  |
| Raise awareness of all STEM resources and collate gathered information to be shared with STEM colleagues across the authority. Development of a spreadsheet containing relevant resources and hyperlinks. | Jill Pringle Alison Kidd | QIO time | From August 2013 Ongoing | Resources being gathered. Looking into a blog as a way to share resources (similar to HTs blog) |
| Plan a range of STEM events to raise the profile of STEM careers available to our young learners to improve communication between future workforce and industry | Jill Pringle Alison Kidd | SDS Global Science Pro Science QIO time STEM DO? | December 2013 |  |
| Produce leaflet/advice note for staff, learners and parents outlining the strategy and the reasons for its existence | Jill Pringle Alison Kidd | QIO time Publications costs | June 2014 |  |
| Work with Edinburgh Science Festival to plan for a STEM engagement day for schools on the Friday preceding the 2015 Edinburgh International Science Festival | Jill Pringle Alison Kidd Karen Prophet | QIO time | March 2015 |  |
| Production of a STEM skills progression framework | STEM DO | DO Time | June 2015 |  |
| Management of a STEM H+S agenda to include management of relevant CPD, policy production and awareness raising at school SLT level | STEM DO Alison Kidd Jill Pringle | DO Time QIO Time | June 2015 |  |
| STEM coordinator meetings 14/15 - Thursday 28th August 2014 Focus on - Context for learning - Working together - Tuesday 25th November 2014 Focus on - Tuesday 10th February 2015 Focus on - Tuesday 28th May 2014 Focus on | Alison Kidd Jill Pringle | QIO time School booking + Catering Various industry/external inputs | June 2015 |  |