Week 1: EV and NM Meeting (virtual over Teams)

- Discuss readiness for IFLE Bronze award.

- Introduce and outline award/ project, using Framework Table document.

- Share expectations and an overview of project using IFLE Bronze Flowchart.

- Share IFLE Framework document, EVs will email document.

- Agree and set all dates between Nursery and EVs.

IFLE BRONZE FLOWCHART – Completed over 20 weeks

Week 2:  Whole Staff Meeting led by EVs ( in person twilight)

- EVs will deliver PowerPoint, discuss framework and facilitate discussion around the indicators.

- Setting must decide on chosen indicators and feedback to EVs. Setting have 1 week to decide.

Week 3: EV and NM Meeting (virtual over Teams)

- NM will feedback selected indicators

Week 4: EV Baseline Observation (EVs, in person, 1/2 day)

- EVs will complete observations around the selected indicators.

Week 5: EV and NM Feedback Meeting- from Baseline Observation (virtual over Teams)

- EVs will share observation summaries in the form of the Action Plan.

- EVs and NM will discuss and record next steps.

- EV will email Action plan to NM, who now has responsibility for implementation and record keeping.

- NM responsible for ongoing gathering of evidence (e.g. photographs, videos, comments, resources, assessment) and beginning PowerPoint and Big Book.

Week 6-11: Setting consolidation

- Staff will implement and begin to embed next steps.

Week 18: Final Observation (EVs, in person, 1/3 day)

- EVs will check in for a progress update, with the NM, with a focus on the accreditation documentation (PowerPoint presentation and Big Book)

Week 12: EV Midway Point Observation (EVs, in person, 1/3 day)

- EVs will complete observations taking account of the next steps.

- NM will share progress of evidence e.g. PowerPoint and Big Book.

Week 13: EV and NM Feedback Meeting- from Midway Point Observation (virtual over Teams)

- EVs will share observation summary, and NM will update the Action Plan accordingly.

- EVs and NM will discuss next steps, and NM will update the Action Plan accordingly.

Week 19-20: Accreditation Visit and Celebration (Accreditors and EVs, in person, 1/2 day)

- Accreditation visit comprising of on floor observation, NM will deliver the PowerPoint presentation, and Big Book.

- Accreditors will reflect and feedback to NM

- Celebration (Week 20)

Week 14-17-: Setting consolidation

- Staff will continue to implement and embed next steps.

- NM will continue to gather evidence for PowerPoint and Big Book.

.