Establishment: Drongan PS

Establishment

Improvement

Plan

2026-27

East

Ayrshire

Council

Education

Service

| School Improvement Plan | Drongan Primary School |
| --- | --- |
| Head Teacher | Tom McFadzean |
| Date Submitted | Submitted to Chief Education Officer on: |

| School / Centre Vision and Values | In Drongan Primary School and Early Childhood Centre our vision for all is: To have a sense of belonging and pride in our local community where everyone is valued and we work together to be the best that we can be. Within our school, ECC and local community, the shared values that we feel are important to instil in all are: Teamwork - Mutual Respect – Trust – Inclusion - Self-belief - Resilience |
| --- | --- |

Checklist

In line with the Standards in Scotland’s Schools etc. Act 2000 (amended 2016), the following checklist is designed to assist Heads of establishment with whole school/centre improvement planning that fulfils statutory duties in accordance with the Act. This must be completed prior to submission.

| SIP Consultation included the following stakeholders: | Complete |  | Content of plan | Complete |
| --- | --- | --- | --- | --- |
| Children and Young People | Yes |  | Takes account of strategic priorities outlined in the Education Service Improvement Plan. https://www.east-ayrshire.gov.uk/Resources/PDF/E/Education-Service-Improvement-Plan.pdf | Yes |
| Parent Council and Forum | Yes |  | HGIOS 4 and EYQF are used as the frameworks to inform the content of SIPs. Where appropriate. https://education.gov.scot/media/v5sh3dqt/frwk2_hgios4.pdf https://education.gov.scot/inspection-and-review/inspection-frameworks/quality-improvement-framework-for-the-early-learning-and-childcare-sectors/ | Yes |
| Teachers, practitioners and ALL school/centre staff | Yes |  | There is clear focus throughout the plan on measures to reduce of inequalities of outcome as a result of socio-economic disadvantage. PEF: https://www.gov.scot/publications/pupil-equity-funding-national-operational-guidance-2023/documents/ CEF: https://www.gov.scot/publications/care-experienced-children-young-people-fund-operational-guidance-2023-24/documents/ SEF: https://www.gov.scot/publications/strategic-equity-funding-national-operational-guidance-2023/documents/ | Yes |
| Volunteers/ Community partners | Yes |  | Appropriate cognisance has been made of the links between the plan and the working time agreement for teaching staff. | Yes |
| Head Teacher / Head of Centre Signature: |  |  | An accessible summary of the SIP is available and contained in this document and will be provided to parents, children and young people. | Yes |

Pupil and parental strategic involvement

| For session 2026-27, please describe below how children and young people will be involved in decisions relating to the operation of the school/centre | For session 2026-27, please describe below how parents will be involved in decisions relating to the operation of the school/centre |
| --- | --- |
| Various pupil committees including Pupil Council, Rights Respecting Schools, Inclusive Practice, Outdoor / ECO and Digital Leaders / Sports Leaders Wellbeing Warriors School leaders including Head / Depute boy and girl, P7 Prefects / Buddies and House / Vice Captain responsibilities in the senior school Pupil focus groups throughout the session focusing on aspects of the improvement plan as well as HGIOS / HGIOURS quality indicators Home circle citizenship assemblies and committee afternoons Daily conversations between children and SLT focusing on wellbeing indicators and values Pupil wellbeing questionnaires focusing on the wellbeing indicators throughout the year – once per term Whole school interactive wellbeing wheel MS Forms focusing on relevant school issues | Engagement with Parent Council Curriculum open afternoons / sharing learning sessions Information sessions Parent curriculum workshops MS Forms / surveys relating to school issues Parents’ Evening feedback SIP consultation Transition events Parent / child play events HT attends Community Council and Community Association meetings |

| Community Plan East Ayrshire 2015 - 2030 | Together, in achieving our Vision, Partners will demonstrate: Effective leadership We will provide clear leadership in Community Planning and engage effectively with our employees and communities Collective ownership We will take collective ownership for delivering on the Community Plan, the associated Single Outcome Agreement and the Community Plan Delivery Plans, and work hard to improve outcomes for local people and communities Good governance We will implement clear operating arrangements to support effective strategic direction, scrutiny and accountability Democratic accountability We will measure and report on the impact of our activities to demonstrate how effectively we are improving outcomes for local people and communities, and all partners will be held to account for their contribution. |  |
| --- | --- | --- |
| Our Partnership will continue to work to meet the needs of the people who live in our communities. Our guiding principles will be reflected in all that we do and should be evident for all to see. |  | We will: - Promote lifelong learning. - Promote equality and tackle inequality; - Adopt a preventative approach; - Ensure effective community engagement in the planning and delivery of local services; - Utilise the strengths and resilience within communities; - Drive efficiency and performance improvement; |

| National and Local Priorities |  |  |
| --- | --- | --- |
| The Scottish Government’s vision for education in Scotland: - Excellence through raising attainment and improving outcomes - Achieving equity Key priorities of the National Improvement Framework: - Placing the human rights and needs of every child and young person at the centre of education - Improvement in children and young people’s health and wellbeing - Closing the attainment gap between the most and least disadvantaged children and young people - Improvement in skills and sustained, positive school-leaver destinations for all young people - Improvement in attainment, particularly in literacy and numeracy | NIF drivers of improvement in the outcomes achieved by children and young people are: - School and ELC leadership - Teacher and practitioner professionalism - Parent/carer involvement and engagement - Curriculum and assessment - School and ELC improvement - Performance information | Scottish Attainment Challenge (SAC) Scottish Attainment Challenge: framework for recovery and accelerating progress Scottish Attainment Challenge Logic Model – Tackling the Poverty-Related Attainment Gap – Our Theory of Change SAC organisers: - Learning and teaching - Leadership - Families and communities |

| East Ayrshire Plans |  |  |  |
| --- | --- | --- | --- |
| Key Priorities | Education Service Improvement Plan: | Children’s Services Plan: | Community Learning and Development Plan: |
| 1: Our Leadership | We actively support, promote and enact leadership at all levels. Our young people are supported to be leaders on their learning in our centres, schools and wider life experiences. All staff have ready access to appropriate CLPL and experiences to promote leadership in every classroom and centre. | Priorities for 2023-26: - Our children and young people feel respected, listened to and influence change - We are working collaboratively, reducing the impact of social and economic poverty on our children and young people - Our children and young people feel safe - Our children and young people have the best start in life - Our children and young people’s mental health is improving | Outcomes: - Growth - Wellbeing - Fairness - Sustainability Action areas - Youth voice and participation - Lifelong learning and skills development - Empowering communities - Wellbeing and inclusion |
| 2: Teaching and Learning Together | Our young people should experience a teaching, learning and curriculum offer that meets their needs, and those of our local and national context. All staff should be supported to deliver in new and innovative ways by accessing CLPL relevant to their needs and those of our young people. |  |  |
| 3: Our Wellbeing and Belonging | We want all of our young people to feel supported by people who know them well, and feel included in all of our schools and centres. Our staff need to be supported in their working with our young people, especially in times of adversity. As a key universal service, it is our vision that all young people attend our establishments on a full-time and regular basis to support them in their development at all stages. |  |  |
| 4: Our Attainment, Destinations and Achievements | We want the very best for all of our young people in East Ayrshire. We aim to ensure all young people secure a positive destination through excellent achievement and attainment at all levels. |  |  |

| Our Leadership: Improvement priority: Provide opportunities for all pupils and staff members to develop leadership skills and take responsibility for effecting change across the school and wider community. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale – Self-evaluation from pupil post survey, highlighted a drop in 6pp of children who feel who feel that they play an important part in the life of the school and contribute to aspects of school improvement. In Drongan PS we want to increase pupil voice for every child and make all children feel valued. Part of this process will be to refresh the Vision, Values and Aims of Drongan PS. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NIF key drivers: | School & ELC leadership |  |  | Parent/carer involvement & engagement |  |  |  | School & ELC improvement |  |  | Performance information |  |  |
| HGIOS4 QIs: | 1.1 |  | 1.2 |  | 1.3 |  |  | 2.7 |  | 3.1 |  |  | 3.3 |
| QF ELC: | Select QI |  | Select QI |  | Select QI |  |  | Select QI |  | Select QI |  |  | Select QI |
| ESIP key priorities: | Y Teaching & Learning |  |  |  |  |  |  | Y Our Wellbeing |  |  | Y Our attainment |  |  |
| Outcomes for our learners |  | Our actions/Approaches/Interventions |  |  |  | PEF | Who |  | Measures |  |  | Review/milestones |  |
| Increase the percentage of pupils who feel that they play an important part in the life of the school and contribute to aspects of school improvement by 10pp from 80% to 90%. |  | - All classes, teachers and support staff will form Class Committees - Class Committee sessions will take place twice per term (minimum) - Class Committees will present at assemblies and displays created demonstrating work undertaken - Pupil Voice assemblies will take place on a regular basis - Pupil focus groups as part of learning observations - Pre survey undertaken with all pupils and staff to establish how much of a voice they feel that they have - Post survey to be completed and analysed to determine impact |  |  |  |  | All staff All staff CTs SLT SLT SLT SLT |  | - Class Committees will be formed - Committee afternoons will have taken place – minimum twice per term - Committees will have presented at whole school assemblies across the session - Home Circle assemblies will have taken place - Pupil Focus Group feedback will be evaluated - Staff members will work with Class Committees - Pupil Survey feedback will demonstrate pupils feel that they have increased voice to impact change |  |  | Termly |  |
| Provide opportunities for all children to influence change and develop leadership skills. |  | - Opportunity to develop leadership, communication and teamwork skills through leading committees. - Provide opportunities for pupils to demonstrate responsibility and commitment to improving their school improvements, through: -Committees -Head / Depute pupils -House Captains / Vice-Captains -P6 Play Leaders -Wellbeing Warriors -Enterprise opportunities -Working with local community |  |  |  |  | All staff CTs CAs SLT Pupils |  | - Improved school and wider community environment – through school initiatives - Pupil suggestions will lead to practical changes - Pre / Post surveys for all stakeholders |  |  | Termly |  |
| Evaluate and refresh the school’s Vision, Values and Aims so that they accurately reflect and respond to the aspirations and needs of the school community. 90% of children will be able to articulate the vision and explain how the values positively impact the school. |  | - Engage with all stakeholders to ensure that all partners have a voice in creating the refreshed Vision, Values and Aims - Questionnaires for pupils, staff, parents/carers, parent council, partners and wider community. - School forum / open afternoon session to engage with whole school community. |  |  |  |  | HT SLT DLT |  | - Completed questionnaires - Feedback from all stakeholders - Revised school Vision, Values and Aims |  |  | October – Consultation complete November – Draft vision / values and aims Jan – Implement and promote May – Evaluate impact |  |

| Teaching and Learning Together: Improvement priority: Improve Engagement in Mathematics within a Thinking Classroom, leading to improved Learning and Teaching experiences across the curriculum. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale – Improving pupils perceptions of mathematics, while increasing their engagement, enjoyment and resilience is essential for developing confident, capable learners. Self-evaluation has highlighted digital technologies and STEM as areas of focus. If used effectively and appropriately, digital technology can enhance learning and teaching, equip our children and young people with vital digital skills and crucially, it can lead to improved educational outcomes. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NIF key drivers: | Teacher & practitioner professionalism |  |  | Curriculum & assessment |  |  |  | School & ELC improvement |  |  | Select driver |  |  |
| HGIOS4 QIs: | 1.1 |  | 1.2 |  | 1.5 |  |  | 2.2 |  | 2.3 |  |  | 3.3 |
| QF ELC: | Select QI |  | Select QI |  | Select QI |  |  | Select QI |  | Select QI |  |  | Select QI |
| ESIP key priorities: | N Our Leadership |  |  |  |  |  |  | N Our Wellbeing |  |  | N Our attainment |  |  |
| Outcomes for our learners |  | Our actions/Approaches/Interventions |  |  |  | PEF | Who |  | Measures |  |  | Review/milestones |  |
| Improve pupils’ perception of mathematics, while increasing their engagement, enjoyment and resilience. Develop learners’ problem-solving skills across the curriculum. |  | - Participation in Thinking Classroom CLPL sessions with Robert McCallum (QIO). - 6 CLPL sessions for all teaching staff - Pre-programme surveys for staff and pupils (Myself as a Learner scale) - Post-programme impact statements from staff and pupils - Classroom observations / quality assurance - School visits from QIO - Development of ‘Thinking Classrooms’ within Drongan Primary School (infant and upper departments). - Purchase resources to support implementation. - Staff will be upskilled in the Thinking Classroom pedagogy. - Opportunities for collaboration with other primary schools within Education Group. - Peer observations / partner collaboration. - Opportunities for staff to visit other establishments to observe good practice. |  |  |  |  | QIO, HTs/Numeracy Lead Teaching staff |  | - Pre and post staff / pupil surveys - Pupil / staff impact statements - Pupils will feel more challenged and more resilient - Professional dialogue with colleagues from other settings to moderate planning, learning, teaching and assessment - Before / after measurements of pupil engagement will demonstrate an increase in enjoyment and resilience. - Staff will report that they are more confident and enjoy teaching mathematics using the Thinking Classroom pedagogy. - Pedagogy from the Thinking Classroom will spread to other curricular areas as teachers become more confident. |  |  | Termly |  |
| Improve the quality of digital technologies and STEM, leading to improved experiences and outcomes for all pupils. Develop technical skills which allow learners and staff to confidently and safely access and create digital materials. |  | - Identification of a Digital Lead staff member - Digital Leaders – pupil group to be formed - Creation of a Digital Skills policy - Purchase of new resources and software to support curriculum development - Implementation of STEM Week, ensuring that every child has the same opportunity to experience new digital technologies and resources - Make use of EAC Lending Library to provide pupils with opportunities to explore a variety of different digital resources - Collegiate working to share practice and develop curriculum - Continue to review digital technologies planner and linked resources - Almost all pupils will state that they enjoy learning experiences provided through digital technologies and STEM |  |  |  |  | Digital lead Pupil Committee CTs CTs SLT CTs All staff Pupils |  | - Increased coverage and depth of BGE - Pupils’ knowledge of potential career pathways and jobs will be enhanced - Pupils will develop their understanding of how digital skills are relevant to their future - Clearer skills progression across all stages - Improved resources and pupil experiences at all levels - Increased staff knowledge and confidence when delivering the curriculum - Pupil surveys – pre and post implementation |  |  | Termly |  |
| Staff will engage with the Scottish Curriculum Improvement Cycle, leading to high-quality learning, teaching and assessment practices. |  | - Staff will engage in national improvements in the curriculum – Curriculum Improvement Cycle (CIC) - Engage in CLPL opportunities when they arise - Provide feedback on sample planners / pathways from the new curriculum |  |  |  |  | All staff |  | - All staff will engage in the development of the Curriculum Improvement Cycle - Staff will provide feedback on samples of the new curriculum when released |  |  |  |  |

| Our Wellbeing and Belonging: Improvement priority: Improve the wellbeing of all children with a specific focus on inclusion and increasing knowledge and understanding of neurodiversity. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale – Self-evaluation and ongoing work with Educational Psychologist has highlighted a need for increasing awareness of social-communication challenges and neurodiversity. End of session pupil surveys showed a continued need for identifying achievements and celebrating successes. Refreshment of inclusive practice has been highlighted as a requirement through self-evaluation. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NIF key drivers: | Teacher & practitioner professionalism |  |  | School & ELC improvement |  |  |  | Performance information |  |  | Parent/carer involvement & engagement |  |  |
| HGIOS4 QIs: | 1.1 |  | 2.4 |  | 2.6 |  |  | 2.7 |  | 3.1 |  |  | 3.2 |
| QF ELC: | Select QI |  | Select QI |  | Select QI |  |  | Select QI |  | Select QI |  |  | Select QI |
| ESIP key priorities: | N Our Leadership |  |  | N Teaching & Learning |  |  |  | N Our attainment |  |  |  |  |  |
| Outcomes for our learners |  | Our actions/Approaches/Interventions |  |  |  | PEF | Who |  | Measures |  |  | Review/milestones |  |
| Improved learning experiences for neurodiverse children. Identified pupils will be able to talk about their achievements and identify their successes. Wellbeing Indicator; 2025/26 Rating (out of 5); 2026/27 Rating (out of 5). Achieving (whole school); 4.3; 4.6. Achieving (ASN pupils); 4.34; 4.6. | - ‘We were expecting you!’ training for all staff in school – delivered by Educational Psychologist (Mark Brotherton) - Modules 1-4 - 4 CLPL sessions for staff across the session - Rights Respecting Schools Committee – pupil group to be formed with lead staff member - UNRC will continue to be a focus throughout the session. - Development of a school ‘Respectful Relationships Policy’ - Improve collective score for ‘Achieving’ Wellbeing Indicator (P4-7 pupils and ASN identified pupils) - Peer sharing best practice sessions to ensure consistent approaches across the school. - Continued promotion of Learner Profiles. |  |  |  |  | Educational Psychologist All Staff SLT Pupil Committee Lead staff member |  | - Staff training is complete - Wellbeing data - Intervention grids - Tracking and monitoring meetings - Identified children will feel that they are achieving in their education - Staff will feel more confident in their practice - Classroom environments will be consistent across the school (displays, resources, settings, etc.) - Paperwork from sharing best practice sessions - Learner Profiles for P4-7 pupils |  |  | Termly |  |
| All pupils will have access to inclusive school environments / classrooms. Wellbeing Indicator; 2025/26 Rating (out of 5); 2026/27 Rating (out of 5). Included (whole school); 4.6; 4.7. Included (ASN pupils); 4.32; 4.7. | - Identification of an Inclusion Lead staff member - Inclusion Committee – pupil group to be formed - Inclusion Committee will lead an ‘Inclusion Week’ in the school. - Review of school ASN Policy and procedures, and transform into school Inclusion Policy - Consistent classroom environments will be evident across the school – resources, displays, language used, etc. - Pupil wellbeing will continue to be tracked termly through their completion of wellbeing webs – with a focus on the included wellbeing indicator - Analysis will provide information for action and next steps - Through HWB programme teachers will provide lessons and guidance with a focus on inclusion - School assemblies will have a focus on inclusion |  |  |  |  | SLT Lead Staff Member CTs CAs Pupil Committee |  | - Pupil Committee will be formed with identified Lead Staff Member - Committee afternoons will have taken place - Committee will have presented at whole school assembly - A more consistent approach across the school will help children feel included - New Inclusion Policy will be created - Pre and post pupil surveys will highlight progress and next steps - Wellbeing data tracked termly |  |  | Termly |  |
| Decrease whole school absences by 1.5% from 7.5% to 6% by June 2027. |  | - Engage with EAC absence procedures - Continue to promote and support attendance - Engage with parents/carers to promote attendance at school - Target identified groups of pupils to focus supports on with aim of increasing attendance (pupils with persistent absence patterns and those less than 90%) |  |  |  |  | SLT |  | - Absences will decrease – shown by data - TWF paperwork with attendance targets/supports evident |  |  | 4 Weekly |  |

| Our Attainment, Destinations and Achievements: Improvement priority: Utilise staff knowledge and expertise, continuing to improve the quality of learning and teaching experiences in writing, to increase attainment at all stages. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale – Using the pedagogy and data from the National Improving Writing Programme, it has highlighted an increase in enjoyment and attainment within writing at targeted stages. The next step is increasing engagement, enjoyment and attainment in writing at all stages from P2-P7. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NIF key drivers: | Teacher & practitioner professionalism |  |  | Curriculum & assessment |  |  |  | Performance information |  |  | Parent/carer involvement & engagement |  |  |
| HGIOS4 QIs: | 1.2 |  | 1.3 |  | 2.2 |  |  | 2.3 |  | 3.2 |  |  | Select QI |
| QF ELC: | Select QI |  | Select QI |  | Select QI |  |  | Select QI |  | Select QI |  |  | Select QI |
| ESIP key priorities: | N Our Leadership |  |  | N Teaching & Learning |  |  |  | N Our Wellbeing |  |  |  |  |  |
| Outcomes for our learners |  | Our actions/Approaches/Interventions |  |  |  | PEF | Who |  | Measures |  |  | Review/milestones |  |
| Increase pupil engagement and enjoyment of writing across the school. Increase attainment in writing for the following stages: Class for 2026/27; 2025/26 EOS Data; 2026/27 Targets. P1 P2 P3 P4 P5 P6 P7; - 75% 75% 82% 77% 82% 78%; 80% 82% 82% 85% 80% 85% 80%. | - Continued participation at the CYPIC National Improving Writing (NIW) sessions (Cohorts 5 & 6): - 2 x 2-hour session for 4 members of staff team - 2 full days (in person) - 5 x 2-hour twilights (virtual) - 2 optional sessions (virtual) - Staff trained in NIW will lead staff CLPL to ensure consistent approaches across the school, ensuring continued focus on high-quality learning and teaching - Review Whole School Writing Overview and Tools for Writing Pathway at Drongan PS - Develop and implement self and peer assessment approaches to provide learners with the knowledge and skills to identify improvements in their own/others’ writing - with a particular focus on Tools for Writing and vocabulary - Collect data regularly on children’s progress with a clear focus on improving one aspect of writing at a time. - Involve children in collecting and analysing data. - Moderation of planning, learning, teaching and assessment improving shared understanding of writing to inform teacher judgements and to identify strengths and next steps for learners - Provide opportunities for parents/carers to engage with the writing pedagogy – open afternoon - Identified pupils will be supported through boost group support and appropriate interventions - Rigorous and robust tracking of pupil progress - SLT and peer observations will take place - Collegiate working providing opportunities to share good practice - Pupil focus groups will provide useful self-evaluation feedback - Increase understanding of the root causes for writing difficulties / barriers (CLPL opportunities) – linked to Inclusion target - Working memory training and CLPL for CAs and SLT |  |  |  |  | P6 & P7 teaching staff and SLT CYPIC National Improving Writing team EA leads: D. McMahon, S. Rae, L. Bull All teaching staff CAs |  | - Pre and Post pupil questionnaires - Regular teacher polls on impact of learning from the NIW programme. - Pareto chart to identify focus for teaching inputs – baseline assessment - Stretch Aim (June 27) for Writing attainment for all classes - 2-3 short-term Teaching Aims for pupils (individuals/groups) for each identified teaching focus. - Run Charts to collect data demonstrating progress daily and share with pupils. - Analysis of Run Charts to learn from data to inform small tests of change and to identify when to move to next teaching aim; provide support; increase challenge - AiFL approaches demonstrate on-going assessment and provide feedback to learners. - Professional dialogue with colleagues from other settings to moderate planning, learning, teaching and assessment. - Pupils’ ability to talk about their progress and next steps both individually and as a class. - Fishbone tool analysis where there is continued non-attainment and consideration of ways to further support pupils. - Writing Benchmarks to support reliability of teacher judgements. - Before /after measurements of pupil engagement will demonstrate an increase in enjoyment of writing. - Staff will report that they are more confident and enjoy teaching writing. - ACEL data in tracking tool |  |  | Termly Tracking Periods |  |

| 2025-26 baseline |  |  |  |  |  | 2026-27 targets |  |  |  |  |  | 2026-27 actual |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Reading | Writing | L&T | Literacy | Numeracy |  | Reading | Writing | L&T | Literacy | Numeracy |  | Reading | Writing | L&T | Literacy | Numeracy |
| P1 | 83 | 75 | 90 |  | 86 | P1 | 80 | 80 | 90 |  | 85 | P1 |  |  |  |  |  |
| P2 | 82 | 75 | 96 |  | 82 | P2 | 83 | 82 | 90 |  | 86 | P2 |  |  |  |  |  |
| P3 | 82 | 82 | 97 |  | 76 | P3 | 82 | 82 | 96 |  | 82 | P3 |  |  |  |  |  |
| P4 | 83 | 77 | 97 |  | 79 | P4 | 82 | 85 | 97 |  | 82 | P4 |  |  |  |  |  |
| P5 | 86 | 82 | 94 |  | 87 | P5 | 83 | 80 | 97 |  | 82 | P5 |  |  |  |  |  |
| P6 | 83 | 78 | 95 |  | 78 | P6 | 86 | 85 | 94 |  | 87 | P6 |  |  |  |  |  |
| P7 | 77 | 74 | 98 |  | 74 | P7 | 83 | 80 | 95 |  | 80 | P7 |  |  |  |  |  |

| Reading | P1 | P2 | P3 | P4 | P5 | P6 | P7 |  | Writing | P1 | P2 | P3 | P4 | P5 | P6 | P7 |  | L&T | P1 | P2 | P3 | P4 | P5 | P6 | P7 |  | Numeracy | P1 | P2 | P3 | P4 | P5 | P6 | P7 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| P1 |  |  |  |  |  |  |  |  | P1 |  |  |  |  |  |  |  |  | P1 |  |  |  |  |  |  |  |  | P1 |  |  |  |  |  |  |  |
| P2 |  |  |  |  |  |  |  |  | P2 |  |  |  |  |  |  |  |  | P2 |  |  |  |  |  |  |  |  | P2 |  |  |  |  |  |  |  |
| P3 |  |  |  |  |  |  |  |  | P3 |  |  |  |  |  |  |  |  | P3 |  |  |  |  |  |  |  |  | P3 |  |  |  |  |  |  |  |
| P4 |  |  |  |  |  |  |  |  | P4 |  |  |  |  |  |  |  |  | P4 |  |  |  |  |  |  |  |  | P4 |  |  |  |  |  |  |  |
| P5 |  |  |  |  |  |  |  |  | P5 |  |  |  |  |  |  |  |  | P5 |  |  |  |  |  |  |  |  | P5 |  |  |  |  |  |  |  |
| P6 |  |  |  |  |  |  |  |  | P6 |  |  |  |  |  |  |  |  | P6 |  |  |  |  |  |  |  |  | P6 |  |  |  |  |  |  |  |
| P7 |  |  |  |  |  |  |  |  | P7 |  |  |  |  |  |  |  |  | P7 |  |  |  |  |  |  |  |  | P7 |  |  |  |  |  |  |  |

Summary of Improvement Plan directly linking to Education Service Improvement Plan

| Our Leadership | Teaching and Learning Together |
| --- | --- |
| Increase the percentage of pupils who feel that they play an important part in the life of the school and contribute to aspects of school improvement by 10pp from 80% to 90%. Provide opportunities for all children to influence change and develop leadership skills. Evaluate and refresh the school’s Vision, Values and Aims so that they accurately reflect and respond to the aspirations and needs of the school community. | Improve pupils’ perception of mathematics, while increasing their engagement, enjoyment and resilience. Develop learners’ problem-solving skills across the curriculum. Improve the quality of digital technologies and STEM, leading to improved experiences and outcomes for all pupils. Develop technical skills which allow learners and staff to confidently and safely access and create digital materials. |
| Our wellbeing and belonging | Our Attainment, Destinations and Achievements |
| Improved learning experiences for neurodiverse children. Identified pupils will be able to talk about their achievements and identify their successes. Wellbeing Indicator; 2025/26 Rating (out of 5); 2026/27 Rating (out of 5). Achieving (whole school); 4.3; 4.6. Achieving (ASN pupils); 4.34; 4.6. Decrease whole school absences by 1.5% from 7.5% to 6% by June 2027. | Increase pupil engagement and enjoyment of writing across the school. Increase attainment in writing for the following stages: Class for 2026/27; 2025/26 EOS Data; 2026/27 Targets. P1 P2 P3 P4 P5 P6 P7; - 75% 75% 82% 77% 82% 78%; 80% 82% 82% 85% 80% 85% 80%. |