2016-2017

Eastwood Cluster Development Plan

Working together to Aspire, Drive and Excel

EHS – 3 Year Plan

| Year 1 | Year 2 | Year 3 |
| --- | --- | --- |
| Numeracy and Maths | Numeracy and Maths | Numeracy and Maths |
| Literacy and Language - Moving Images | Literacy and Language | Literacy and Language |
| Health and Wellbeing - Science (transitions) - BECS (transitions) | RME | Transitions |
| Maximising Attendance | Social Studies | Science |
| ELCC | Modern Languages | Expressive Arts |
| DYW | DYW | DYW |
| GLOW | Health and Wellbeing (progression) | Technology |
| HGIOS4 Self- Evaluation | HGIOS4 Self- Evaluation | HGIOS4 Self- Evaluation |

| Leadership and Management |  |
| --- | --- |
| How good is our leadership and approach to improvement? |  |
| Quality Indicator | Themes |
| 1.1 Self-evaluation for self-improvement | - Impact on Learners’ Successes and Achievements |
| 1.2 Leadership of learning | - Professional engagement and collegiate working - Impact of career-long professional learning |
| 1.3 Leadership of change | - Developing a shared vision, values and aims relevant to the school and its community |
| 1.4 Leadership and management of staff | - Building and sustaining a professional staff team |
| 1.5 Management of resources to promote equity |  |

|  | Outcome/ Impact | Action | Responsibility | Timescale | Resources | Monitoring/ Evaluation | GIRFEC | Capabilities |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Senior leaders provide strong leadership that promotes and sustains our aspirational vision All staff show commitment to the shared educational values of the cluster | - Share the draft vision for the cluster - Consult with all stakeholders and review and adapt as appropriate - Learners are supported to understand the vision aims and values through the four contexts for learning | All | Term 1 | Cluster Glow Site Assembly Programmes | Staff, Pupil and Parent Feedback | Included | Community Engagement |
| B | Staff engage regularly in professional dialogue to develop collective understanding The cluster has a range of effective systems and structures to facilitate regular collegiate working Staff are confident in discussing how they have improved their practice as a result of their professional learning activities | - Share cluster Glow group at August in-service - Rights Respecting School good practice guide - Numeracy and Mathematics (fractions) - Science - Literacy and English (reading and talking & listening) - Further develop cluster programme of CLPL opportunities in areas such as ICT and DYW and including CLPL Cluster Newsletter | CPD Coordinators Education Officer – Assessment and Moderation Moderation Facilitators | Term 1 Term 2 & 3 | Cluster Newsletter Cluster Glow Site LAR | Gateway PRD Meetings CLPL Evaluations Moderation Event Evaluations | Achieving | Modernising The Way We Work |
| C | Staff will work to ensure that there is an Impact on learners successes and achievements | Our self-evaluation will focus on key aspects of learners’ successes and achievements to show clear evidence of improvement based on actions taken as a result of self-evaluation. All stakeholders, including children and young people, will have shared ownership of this evidence and use it to plan continuous improvement | Head Teachers Depute Head Teachers PTs | On-going | HGIOS4 | CMG Meetings Minutes from Cluster meetings | Included Responsible Achieving |  |
| D | Pilot Maximising Attendance Policy on a Cluster basis | Reduce Absence Statistics and manage staff absence more efficiently | CMG Business Managers (TBC) Donna Clark Claire Shaw Margaret Hay | Termly CMG | Time | CMG Meetings Minutes from Cluster meetings |  |  |

| Learning Provision |  |
| --- | --- |
| How good is the quality of care and education we offer? |  |
| Quality Indicator | Themes |
| 2.1 Safeguarding and child protection |  |
| 2.2 Curriculum | - Learning Pathways |
| 2.3 Learning, teaching and assessment | - Planning, tracking and monitoring - Learning and engagement |
| 2.4 Personalised support | - Universal support |
| 2.5 Family learning | - Quality of family learning programmes |
| 2.6 Transitions | - Collaborative planning and delivery |
| 2.7 Partnerships | - Impact on learners |

|  | Outcome/ Impact | Action | Responsibility | Timescale | Resources | Monitoring/ Evaluation | GIRFEC | Capabilities |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Literacy and English | Learning pathways support children and young people to build on their prior learning and ensure appropriate progression for all learners Learning pathways are based on the experiences and outcomes and design principles of depth, progression, coherence, breadth, personalisation and choice, challenge and enjoyment and relevance | - Implement and evaluate curriculum mapping to ensure consistent pace of learning whilst ensuring breadth, challenge and application across the BGE - Talking and Listening – 3rd & 4th - Reading Nov 16 - Formulate a curriculum map for Writing to ensure consistent pace of learning whilst ensuring breadth, challenge and application across the BGE. Sept 16 - Support Cluster Staff in the preparation of materials relating to the cluster moderation event (Writing, Talking and Listening and appropriate bundling of Es and Os). Cluster GLOW materials for listening. Nov 16 - Evaluate analysis of cluster motivation and attitude survey (2015-16). Formulate action plan based on evidence gathered and incorporate CLPL on Moving Image Education. Share on Cluster GLOW. | Catherine Dillon-Ruddy Education Officer – Assessment and Moderation Moderation Facilitators | Termly November School Event February Cluster Event By June 2017 | Progression Frameworks Advancing Excellence and Equity paper £2400 for cover | Cluster Glow site Minutes of meetings School QA activities | Achieving | Data, Evidence and Benchmarking |
| Numeracy and Maths | Raising attainment of lowest performing 20% of pupils in the area of numeracy and mathematics Parents and carers are supported to actively and meaningfully engage in their children’s learning within the context of mathematics Practitioners develop skills in implementing a CGI informed approach Process of assessment and moderation helps to inform teacher judgements and next steps in learning. | Track pupils attitude and attainment in maths through questionnaires, assessments, teacher judgements and standardised test information. To engage parents of the target group to enable them to support their children at home, including the wide range of strategies and incorporating the common language and methodology. Practitioners plan problem solving approach informed lessons, implement and evaluate. Assessment and Moderation of problem solving approach based lesson with identified Experiences and Outcomes, using the significant aspects of learning and progression framework. | F Loudon Working Group School improvement partnership Moderation Facilitator | Aug ’16 – March ‘17 Nov ‘16 March ‘17 May ‘17 | Tracking Database Progression Framework Advancing Excellence and Equity paper National Improvement Framework £1200 for cover | A group of pupils will be tracked and monitored in each school across the cluster Evaluation by parents following targeted work Evaluation of strategies used and common language and methodology Assessment and moderation led by moderation facilitator Final Report | Achieving Attaining Attainment and Achieving | Data, Evidence and Benchmarking Prevention Community Engagement |
| Early Years | To raise attainment within Baseline Assessment and Developmental Milestones results in p1. At key milestones, our assessments provide reliable evidence which we use to report on the progress of all children and young people. Our assessment evidence is valid and reliable Parents and carers are supported to actively and meaningfully engage in their children’s learning and life within Early Learning and Child Care and transitioning into primary1. | Audit strengths and development areas identified through current data from Baseline and Developmental Milestones. Share good practice on: - Alliteration - Rhyme - Counting and Matching - Position of Number in a Sequence - Gross and Fine Motor Skills Plan and implement opportunities to engage families in learning - BookBug - Read Write Count - Book Bags and Story Sacks - Science Bags - Rhyming Bags - Woodland Explorers | Rosemary Crossan Julie MacLaren | By Oct 2016 Oct 16-May 17 Oct 16-May 17 | Tracking Database Progression Framework National Improvement Framework Working group key workers Staff observations £400 for resources Parental feedback |  | Attaining | Data Evidence and Benchmarking Prevention Community Engagement |
| Transitions | Increased Opportunity for Active Learning in Science Es and Os to improve Skills Development Consistent approach and recording and sharing of Transitions Information To develop a partnership project with cluster primaries and secondary with a specific focus on improving problem-solving skills, using equipment and software and making connections between specialised skills within DYW | Science champions and PT Science EHS to identify and provide CLPL opportunities for Staff. A series of joint lessons delivery agreed and undertaken. - Evaluate Transition Policy/Programme - Share examples of good practice in Pastoral Notes - Relevant Staff to attend CLPL when available Within the context of the Micro:Bit (BBC) introduction to basic coding. Moderation be incorporated into the project Inclusive cluster sports event – netball, hockey, football, badminton | Science champions and PT Science EHS Cluster HTs | By June 2017 | Time for meetings and team teaching EWH Cluster Transition Policy/ Programme Children and Young People’s (Scotland) Act 2014 Cluster newsletter for CLPL DYW implementation plan £445 Funding Bid Active Schools Young Leaders | Transitions Working Group and CMG Feedback Evaluations | Achieving Active | Modernising how We Work |

| Successes and Achievements |  |
| --- | --- |
| How good are we at improving outcomes for all our learners? |  |
| Quality Indicator | Themes |
| 3.1 Ensuring wellbeing, equality and inclusion |  |
| 3.2 Raising attainment and achievement | - Overall Quality of Learners’ achievement |
| 3.3 Increasing creativity and employability | - Digital literacy - Increasing employability skills |

|  | Outcome/ Impact | Action | Responsibility | Timescale | Resources | Monitoring/ Evaluation | GIRFEC | Capabilities |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C | As learners move through their learning pathways they take increasing responsibility for ensuring they continue to add value to their achievements. | There is evidence that children and young people are applying and increasing their achievements through active participation in their local community. Track achievements using the Tracking Database and the 4 Contexts for Learning. | CMG Joe McCaig QIO | By June 2017 | Tracking Database | CMG meetings Tracking database | Responsible Achieving Included | Digital Data, Evidence and Benchmarking |
| DYW B | Identify areas within cluster DYW provision requiring development in each school and across all schools Increase the number and range of business partnerships in Cluster Schools Enhance Skills for work development, such as problem solving, team work and leadership | Collate and analyse results from Cluster Audit undertaken in 2015/2016 Formulate action plan Engage with West Hub and parents to secure al least one business partner for each school Re-introduce and update the Cluster K’nex Challenge | S Maxwell G Boyle Cluster Working Group Cluster Working Group EHS Technical Dept | By Oct 2016 By April 2017 May 2017 | N/A Posters (DYW) West Hub Updated K’nex Kits £500 Printing Budget | Working Group Working Group Pupil Evaluations Teacher Observations | Included, Active Achieving Respect Responsible A | Community Engagement Prevention Maximising How We Work |

Eastwood High School Cluster

Curriculum Development Audit

| 2011 | 2012 | 2013 | 2014 | 2015 |
| --- | --- | --- | --- | --- |
| Social Subjects | ICT | Science | Science | Science |
|  | RME | Technologies | GIRFEC | Transition |
|  | Writing |  | Assessment & Moderation | Assessment & Moderation |
|  |  | French | French | Motivation Reading |
|  |  | Listening & Talking | Listening & Talking | CGI – N&M |