Cart Mill Family Centre

Improvement Plan

2025-2026

| Three Year Improvement Priorities |  |  |
| --- | --- | --- |
| Centre Improvement Priorities for 2025-28 |  |  |
| Year 1 2025-2026 | Year 2 2026-2027 | Year 3 2027-2028 |
| Leadership Introduce Quality Improvement Framework Cluster Professional Learning Refresh Our Values- what matters to us now? | Quality Improvement Framework embedded in QA and practice Practitioner Inquiry approach developed, linked to professional learning and Quality Conversations Embed our refreshed Values | Practitioner Inquiry approach embedded using Quality Improvement Framework Implementation of recommendations from curricular review (Curriculum Improvement Cycle) |
| Children Play and Learn PANECAL Accreditation, utilising Up, Up and Away strategies Introduce Meta-skills Journey towards RRS Silver award | Embed Meta-skills during planning Use digital technologies to enhance learning as we work towards Digital School Award | Further develop innovative and creative resources and experiences, including digital technologies Rights Respecting Gold Award |
| Children Thrive and Develop in Quality Spaces Cluster Risk Assessment Approach Children experience safe, secure and inspiring environment outdoors. | Forest Kindergarten Sessions Learning for Sustainability Self-Evaluation Framework Continue to build on developing the environment outdoors (interaction, spaces and experiences) | All RA updated and embedded, using child friendly language and SIMOA Embed Learning for Sustainability |
| Children are Supported to Achieve Further develop approaches to inclusion and equality, ensuring effective targeted and universal supports, leading to improved outcomes for children and families Gold Family Centre Reaccreditation | Continue to develop and embed innovative approaches to inclusive practice and personalised support Keeping the Promise | Embed approaches to inclusion and equality, ensuring effective targeted and universal supports, leading to improved outcomes for children and families Keeping the Promise |

Our Vision, Values and Aim

Cart Mill Family Centre aims to be the best place for children to learn and develop. We provide an exciting curriculum which puts the child at the centre of learning. We will through striving for excellence in all that we do enable children to become, successful learners, confident individuals, responsible citizens and effective contributors. We seek to: - - Provide safe, secure, healthy and stimulating learning environments. - Promote each child’s self-esteem and encourage positive attitudes towards themselves and others. - Ensure each child receives an appropriately child centred, broad and balanced curriculum. - Foster genuine partnership with parents and carers. - Enable each child to reach their full potential by carefully listening and responding to them. - Implement effectively national and local policies. - Ensure all resources are easily available to children and are natural whenever possible. - Use the outdoor spaces to extend and enrich children's learning. - Work in partnership with the wider community. - Celebrate all forms of achievement. - Ensure our Family Centre provides an ethos of trust, where childhood is viewed as a free, innocent, special time of life, where children are encouraged to be inquisitive, explore and have fun. Cart Mill Family Centre Charter We pledge to- - Respect and Engage Get it Right for our Children and Families (GIRFEC) - Update Staff Training and Knowledge Provide Feedback and Share our Actions - Track and Reflect Embrace working with our Families - Be Part of our Community Promote Equity and Diversity - Remove Barriers and Seek Solutions Plan for Curricular Areas in Learning Programmes

s

| How good is our leadership and approach to improvement? |  |
| --- | --- |
| Leadership and Management Improvement Priority: Develop shared understanding of ‘A Quality Improvement Framework for the Early Learning and Childcare Sectors’ to enhance children’s experience |  |
| NIF Priority: - Placing the human rights and needs of every child and young person at the centre of education. - Closing the attainment gap between the most and least disadvantaged children and young people. - Improvement in children and young people’s health and wellbeing. - Improvement in skills and sustained, positive school-leaver destinations for all young people. - Improvement in achievement, particularly in literacy and numeracy. | QIs: Leadership and management of staff and resources (CI) - Vision, values and aims - Self-evaluation, quality assurance and implementing change. - Staff recruitment and induction Staff skills, knowledge, values and deployment (CI) - Staff skills, knowledge and values - Staff deployment Leadership for continuous improvement (ES) - Pedagogical leadership - Leadership and professional learning - Planning and continuous improvement |
| NIF Driver(s): - School and ELC leadership - Teacher and practitioner professionalism - Parent/carer engagement and family learning - Curriculum and assessment - School and ELC improvement - Performance information | LIP – Expected Outcome / Impact: Empowerment and leadership Pedagogy and Learning Social Justice and Wellbeing Attainment, Achievement and Progress |

| Expected Impact & Outcomes (Measurable, impact, who, how many and when?) | Actions (What we will do/planned activities) | Personnel (person leading) | Timescale (specific terms/months) | Resources (resources/budget/costs/training) | Monitoring & Evaluation (How will you monitor impact and evaluate progress?) |
| --- | --- | --- | --- | --- | --- |
| All staff are familiar with the content and structure of the new shared Quality Framework and begin to use this to improve outcomes for children by September ’25. All staff understand their responsibility in improvement through self- evaluation using the new Shared Quality Framework and utilise this to improve children’s experiences by March ‘26. All staff to use Quality Improvement Framework to reflect on their practice and identify areas for improvement. All children, staff and families to be involved in the creation of our values, considering what matters to use as a community. Staff share expertise and support each other to enhance their practice. | Whole Team training on new Quality Improvement Framework All staff to attend CLPL on QIF and methodology and shared understanding of self-evaluation. Using Quality Improvement Framework for self-evaluation alongside children and families. Utilise challenge questions each month to familiarise all stakeholders with language of new framework and ensure our quality assurance approaches positively impact children’s experiences. All staff use Quality Improvement Framework to reflect on their practice and identify areas for improvement. Create meaningful and manageable self-evaluation approaches using new documentation. Creation of values, important to Cart Mill Recognise, celebrate and utilise the range of staff skill, expertise and knowledge across all staff groups. Encourage staff to share knowledge and expertise with each other by displaying staff qualifications and information about their enhanced knowledge and areas of expertise in a prominent area of the centre. | HT DHC All staff across cluster All staff HT DHC SCDOs | Aug/ Sept ‘25 April ‘26 By October 25 By October 25 | Quality Improvement Framework ERC resources Local Authority Leads Education Scotland/ Care Inspectorate methodology training Self-evaluation floorbooks Children’s voice to evaluate and inform Marbles in a jar Quality Assurance calendar QR codes for feedback on challenge questions: How are we doing? How do we know? Next steps… You said… We did…and then we… Weekly Cart Mill Chat Parent’s WhatsApp Group Parent Group Representatives QR code Questionnaire | Evidenced during Quality conversations An increase in all staff’s confidence and understanding of using the new Quality Improvement Framework. Questionnaire to all staff in August 25. Comparable questionnaire in Term 4 to measure impact and staff confidence. Results may impact SIP 26-27 All children, staff and families refer to our values. Staff photos and areas of leadership displayed. |

| How good is the quality of care and learning we offer? |  |
| --- | --- |
| Children Play and Learn Priority: Create spaces and experiences to increase opportunities for Literacy and STEM during continuous provision. |  |
| NIF Priority: - Placing the human rights and needs of every child and young person at the centre of education. - Closing the attainment gap between the most and least disadvantaged children and young people. - Improvement in children and young people’s health and wellbeing. - Improvement in skills and sustained, positive school-leaver destinations for all young people. - Improvement in achievements particularly in literacy and numeracy. | QIs: Play and Learning (CI) - Children’s engagement - Quality of interactions - Child-centred Planning and Assessment Curriculum (ES) - Curriculum Rationale and Design - Continuity and Progression in the Curriculum - Partnerships - Skills for Life and Learning Learning Teaching and Assessment (ES) - Children’s experience and spaces - Interactions to support learning - Planning and Assessment - Tracking and Monitoring |
|  | Children Experience High Quality Spaces (CI) |
|  | - Quality, Safety and Management of Spaces - Children influence and Affect Change. - Information Management |
| NIF Driver(s): - School and ELC leadership - Teacher and practitioner professionalism - Parent/carer engagement and family learning - Curriculum and assessment - School and ELC improvement | LIP – Expected Outcome / Impact: Empowerment and leadership Pedagogy and Learning Social Justice and Wellbeing Attainment, Achievement and Progress |

| Expected Impact & Outcomes (Measurable, impact, who, how many and when?) | Actions (What we will do/planned activities) | Personnel (person leading) | Timescale (specific terms/months) | Resources (resources/budget/costs/training) | Monitoring & Evaluation (How will you monitor impact and evaluate progress?) |
| --- | --- | --- | --- | --- | --- |
| All practitioners have a shared understanding of effective learning, teaching and assessment and use this to facilitate high quality learning experiences for children. All practitioners feel empowered to evaluate and improve practice in Literacy and STEM All children are supported to develop their skills for life and learning, and an awareness of the world in which they live and grow. All children explore, experiment, and develop a range of meta skills for example, curiosity, creativity and confidence. All children can select and use appropriate technology to learn or solve problems through play and real-life contexts. All children can articulate their rights within a supportive, nurturing environment in a developmentally appropriate way. | All staff, children and families to engage with PANECAL process. Nursery Teacher Cluster Group to continue moderation and reflective collaboration on children’s progress and experiences, focus on Literacy. Cluster Inset Day CLPL on ERC linking to ERC tracking tool. Robust discussions about children’s learning to make sound judgements about progress with a particular focus this session on N5 children. CLPL opportunities for staff to understand and explore meta-skills. Increase staff confidence in planning experiences and spaces which develop curiosity, creativity and confidence. Linking meta skills to children’s learning journals, in a developmentally appropriate Link in with cluster gradient of learning Children involved in meaningful next steps linked to Meta Skills. Increase opportunities for staff and children to introduce film and screen curriculum Introduce AI with staff and children to help design new garden for 3-5s and The Pond. Creation of STEM Working Party Staff utilise technology to enhance children’s creativity, thinking and learning Conduct informal, play-based activities to explore children’s understanding of rights (e.g., “What do you need to feel happy and safe?”) Rights Steering Group formed (children, staff and parents) Increase child participation in daily routines and decision-making (Article 12). Enhance staff knowledge of rights through monthly focus on articles. Create Charter to link with re-freshed Family Centred Approaches Charter Update policies with UNCRC rights, child voice and parent/carer comment Strengthen links with families around UNCRC awareness through weekly Cart Mill chat. | Siobhan Drummond (Educational Psychologist) HT All Staff Literacy Working Group Nursery Teacher Group across Williamwood Cluster Cluster leads Eilidh (STEM Lead) STEM Working Party Derek (RRSA Lead) HT SCDOs DHC | By Nov 25 October Inset Day By May ‘26 By April 2026 By May 26 Ongoing By Jan 26 | PANECAL Self-Evaluation Framework. £200 dual language books £200 cultural festival books Photos and videos Venue to hold 100 CDOs Any identified resources to improve provocation, experiences and continuous provision as relevant. Data from previous years DMs in P1 DYW resources My World of Work Meta-skills framework CfE 4 capacities Resources from Digihub Resources from ERC STEM CLPL £1000 to replace resources Select with children which resources they would then like to purchase. ERC ‘Froebel Friends’ Liaise with Caroline Collins (PT STEM & Learning for Sustainability £150 RRS Annual Membership Silver RRS Guidance Framework ‘How to achieve Silver: Rights Aware’ E-learning David Gordon QIO Steven Kidd UNCRC Senior Professional Adviser (Scotland) Silver RRSA CLPL UN Sustainable Development Goals | Utilise PANECAL self-evaluation framework. Literacy environmental audits, engagement levels and feedback questionnaires. Individual Developmental milestone data shows a steady increase in achievement. Increase data from June 25 ERC Tracking: 48% write name with capital and lowercase correctly 61% can recognise initial sounds and find other words beg. with same sound Staff confidence questionnaire (revisit May 26) Verbatim feedback Tracking Data Feedback forms Evidence of children’s voice, using meta-skills language in Learning Journals Learning Journal Monitoring ERC Tracker Audit Tracking Meetings Minutes of Planning Meetings Parent questionnaire Children are able to describe their learning using meta-skills terminology. Staff confidence questionnaire (revisit May 26) Action Plan working towards Digital Award ERC digital Strategy RRSA baseline questionnaire RRSA Action Plan RRSA Self-Evaluation Floorbooks, drawings and rights-based display show how children are aware of and practice their rights. Digital portfolio with photos, quotes, planning samples, and reflections. Silver RRSA accreditation team feedback |

| How good are we at ensuring the best possible outcomes for all our children / learners? |  |
| --- | --- |
| Priority: All staff meet the needs and entitlements of all children and families, with a particular focus on equity, equality, inclusion and diversity. |  |
| NIF Priority: - Placing the human rights and needs of every child and young person at the centre of education. - Closing the attainment gap between the most and least disadvantaged children and young people. - Improvement in children and young people’s health and wellbeing. - Improvement in skills and sustained, positive school-leaver destinations for all young people. - Improvement in achievement, particularly in literacy and numeracy. | QIs: Nurture Care and Support (CI) - Nurturing Care - Personal Planning - Connections with Families Wellbeing, Inclusion and Equality (ES) - Positive Relationships and Wellbeing - Universal Support - Identification of Learning Needs and Targets - Inclusion and Equality Children’s Progress and Achievements (ES) - Progress over Time Across all Areas of Learning - Overall Quality of Children’s Achievements - Ensuring Equity for all Children Safe Guarding and Child Protection (ES and CI) - Arrangements for Safeguarding including Chid Protection - Children are Safe, Secure and Protected from Harm - National Guidance and Legislation |
| NIF Driver(s): - School and ELC leadership - Teacher and practitioner professionalism - Parent/carer engagement and family learning - Curriculum and assessment - School and ELC improvement - Performance information | LIP – Expected Outcome / Impact: Empowerment and leadership Pedagogy and Learning Social Justice and Wellbeing Attainment, Achievement and Progress |

| Expected Impact & Outcomes (Measurable, impact, who, how many and when?) | Actions (What we will do/planned activities) | Personnel (person leading) | Timescale (specific terms/months) | Resources (resources/budget/costs/training) | Monitoring & Evaluation (How will you monitor impact and evaluate progress?) |
| --- | --- | --- | --- | --- | --- |
| The needs of all children are met through activities which support prevention and early intervention, improve outcomes and reduce inequalities Children’s needs are identified early through careful observation and timely, appropriate interventions are put in place Through effective partnership working, we are improving young children’s development and learning and are securing positive impacts for children and families in our community. | All staff to take part in CLPL around inclusive practice: - ‘Up, Up and Away’- creating an inclusive environment - TURAS Trauma Informed - ‘Keeping the Promise’ - PANECAL strategies - UNCRC Rights Respecting - ‘Cost of the School Day’ Refresh Gold FCA Self-Evaluation and Action Plan All families involved in reviewing charter with UNCRC links Introduce skills based ‘Stay and Play’ sessions Relaunch Parent Group Introduce Coffee and Chat/ Walk and Talk group | All staff led by DHC, ‘Up, Up and Away’ lead All staff led by DHC Val MacLean FCA and Parental Engagement Lead HT | Term 1 and Term 2 By Nov 25 | Ed Psych team ‘Up, up and Away’ PANECAL resources TURAS Training Promise and Child Protection Training Karen Stevenson (PT: Inclusive Practice and Whole Family Support) ‘Cost of the School Day’ Audit Family Centred Approaches framework David Gordon (QIO) TURAS Breastfeeding Friendly CLPL | Annual CLPL Calendar In-service day plans CLPL evaluations Wellbeing Plans Universal supports overview Leuven Scale Observations and Overview Family Centred Approaches (FCA)) Gold Self-Evaluation FCA Action Plan Reaccreditation Feedback |

| Expected Impact & Outcomes (Measurable, impact, who, how many and when?) | Actions (What we will do/planned activities) | Personnel (person leading) | Timescale (specific terms/months) | Resources (resources/budget/costs/training) | Monitoring & Evaluation (How will you monitor impact and evaluate progress?) |
| --- | --- | --- | --- | --- | --- |
| All children embrace a benefit-risk approach within their play experiences to challenge and extend their learning. All children are safe and their opportunities to enjoy challenging and fun play experiences are not compromised. All children experience safe, secure and inspiring environment outdoors. All children have opportunities to learn about sustainability and caring for their natural environment. 100% outdoor environment used by staff and children. | Staff understand and share appropriate risk assessments BSA and Senior CDO EY group Create RA and audit overview Staff continue to receive robust training on infection prevention and control measures. Staff have clear understanding and confidence to provide and promote high-quality, clean, safe environment. Garden areas redesigned AI used to create possible plans Children, staff and families invited to share ideas Garden design installed. Upkeep of garden planned to ensure sustainability | All staff Cluster Group BSAs, BSM and SCDOs HT Garden Staff All children Helen Cross (local author & school garden champion) | Aug- Dec Aug-Nov | ‘Setting the Table’ ‘Advanced Allergen Training’ Food Standards Scotland Infection Control ERC H&S overview ERC EYs Development Officer (Keeping children safe: Practice notes). CI and TURAS– SSSC £tbc re budget reserves Local landscape company (procurement for best value) ‘Space to Grow and Thrive’ ‘Realising the Ambition: Being Me’ ‘Learning for Sustainability’ UN Sustainable Development Goals | Audits Quality Assurance Calendar New Framework Challenge questions Evidence of children’s involvement with SIMOA when RA Garden Floorbook Before & after photos Voting for ideas Garden Plans from landscaping companies ERC H&S weekly playground monitoring |