Strathkinness Primary School

School Improvement Planning and Pupil Equity Fund Planning

Session 2023-2024

Session 2023 -2024 Improvement Plan

| Focused Priority 1: Develop whole school approach to teaching maths Pupil version: Improve the way we learn maths |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| National Improvement Framework Priority |  |  | HGIOS4 Quality Indicators |  |  |
| - Improvement in attainment – particularly literacy and numeracy - Closing the attainment gap between the most and least disadvantaged children and young people |  |  | 1.3 Leadership of Change 2.2 Curriculum 2.3 Learning Teaching and Assessment 3.2 Raising Attainment and Achievement |  |  |
| Expected Impact | Strategic Actions Planned | Responsibilities |  | Measure of Success (Triangulation of Evidence/QI Methodology) | Timescales |
| Increased teacher efficacy for all teaching staff Increased positive mathematical mindsets in focus group of pupils Increased levels of engagement in learning journey for focus group of pupils Increased clarity for parents/carers of school approach to mastery learning in maths , Increased maths attainment in P4-5 cohorts. | Whole school approach to teaching maths – Maths No Problem Embed staff training (MNP, Jo Boaler), moderation processes, assessment and peer support into collegiate calendar Staff, pupil and parent survey to plan training/communications and measure impact Opportunities to apply mathematical skills in range of contexts to develop their flexibility in mathematical thinking and problem solving. Careers week – STEM focus day. Identification and tracking of focus groups Audit resources to ensure high quality lesson delivery Open afternoon, pupil to parent presentations, MNP communication. Consider approaches to home learning to incorporate problem solving and mathematical thinking approaches. | Working party - Audits, surveys, moderation, Stage partners for peer support activities HT – collegiate calendar and parent links Pupil committees – presenting and communicating to stakeholders. HT and CT for P4-5 cohorts |  | Attainment over time evidence in long term to measure impact of consistent approach to teaching maths. Surveys to measure positive mindsets and engagement in focus group in each class Assessment evidence to track attainment of focus group in each class Moderation against Benchmarks Peer support dialogue evidences increased teacher efficacy Track assessment of P4 and P5 cohorts to evidence increased attainment.(P5 in SK) Parent surveys and open day feedback measurement LP Visit | Prior to summer holiday ensure all staff can log on and familiarise with resource Create working party and action plan by end of week 2 including peer support plans INSET 2 initial training – further training sessions planned within collegiate calendar MNP letter out to parents Maths display and survey for parents at Parent Teacher Interview night Term 1 weeks 6 and 7 Open event for parents Term 2 By end of November – plan during INSET Identification of focus groups by week 4 Term 3 engage with wider community to provide context for application of maths skills – university links? Career week STEM Day? Home learning maths policy by end of term 3. September and February tracking meetings for P4. |

| Focused Priority 2: To embed a streamlined, bespoke Assessment Strategy that incorporates Support for Learning – universal and additional Pupil Version: My assessments support my learning journey. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| NIF Priority - Improvement in attainment – particularly literacy and numeracy - Closing the attainment gap between the most and least disadvantaged children and young people - Placing the human rights and needs of every child and young person at the centre of education |  | HGIOS 4 Quality Indicators 2.2 Curriculum 2.3 Learning, teaching and assessment 2.4 Personalised support 3.2 Raising Attainment and Achievement |  |  |  |
| Expected Impact | Strategic Actions Planned |  | Responsibilities | Measure of Success (Triangulation of Evidence/QI Methodology) | Timescales |
| All staff will use a consistent approach to assessment eg what to use and when. Leading to appropriate pace and challenge in learning and effective tracking and monitoring. All teachers feel supported in planning and tracking by robust, triangulated evidence that clarifies and supports their professional judgement. All staff follow the Assessment and Planning for ASN procedure when an unmet need is identified. A more efficient and timely ASN referrals process. All pupils receive the appropriate internal/external support in a timely manner. | Finalise and embed assessment calendar with links to digital master copies/ relevant resources. Revisit during staff meetings to ensure being used in all classes. All cohorts to have individualised assessment folder. Tracking meetings evidence to support assessments. Analyse and compare summative and formative data. Embed Assessment and Planning ASN procedure for use by all teaching staff. Timetabled hours for LST discussions. Quality Assurance focus on targeted cohorts/groups. All ASN pupils have an updated Pupil profiles/summary of support – to be added to Pupil One Note. Clear review timetable planned for all ASN pupils across the session. |  | HT and all staff LST/CT/PSA HT/PT/LST HT/CT SLT and working party HT/PT/LST HT/PT/CT/LST/PSA HT/PT/LST/CT/PSA HT/PT/CT/LST | LP visits Peer/HT observations Quality assurance procedures Evidence folders Planning/Tracking/Evaluation meetings Self-triangulation of evidence eg NSA, end of level assessments, ongoing formative assessments – does it match tracking? | August to September plus ongoing throughout session – update at tracking meetings/LS meetings and staff meetings Assessment folders in place by August Tracking meetings and LS meetings as per Collegiate Calendar HT/LS meetings termly All ASN pupils will have review by June 24 |

| Focused Priority 3: Improving Feedback, self and Peer Assessment in Writing Pupil version: I know more about how well I am doing in my writing. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| NIF Priority - Placing the human rights and needs of every child and young person at the centre of education - Improvement in attainment, particularly in literacy and numeracy |  |  | HGIOS 4 Quality Indicators 2.2 Curriculum 2.3 Learning, teaching and assessment 2.4 Personalised support |  |  |
| Expected Impact | Strategic Actions Planned | Responsibilities |  | Measure of Success (Triangulation of Evidence/QI Methodology) | Timescales |
| Pupils will develop approaches to peer and self-assessment in writing which will lead to improved understanding of their progress and next steps Consistent and progressive approach across school which will provide a framework for further development of peer and self-assessment All teachers provide individual feedback for pupils in writing in an agreed format | Use of Fife Writing Assessment Pack resource for Peer and Self-Assessment Audit of pupils to gain baseline of level of understanding and skills around self and peer assessment as well as measure how well they understand their progress and next steps in writing Agreed approach to peer and self-assessment at Early, First and Second levels that has clear progression Agree and implement approach to marking writing that provides quality feedback for pupils and evidence of progress | Teaching staff Working party Working party and teaching staff Working party and teaching staff |  | Survey evidence from pupils Evidence from learning partnership on pupil skills in talking about progress and next steps Examples of peer and self assessment – baseline evidence gather in term 1 then moderate in term 3 and evaluate in term 4. Evidence of feedback in jotters/pieces of writing that links to SC, text, further work. Moderated across school. | Early term 1 and early term 4 Term 3 Term 1 and 3 Throughout session as part of QI |

| STRATHKINNESS PRIMARY |  | TOTAL PEF: £5403 |  |  |
| --- | --- | --- | --- | --- |
| Attainment Fund Rationale To support pupils who have barriers to learning. |  | Amount of Fund: £5403 |  |  |
| We have an identified group of pupils who are experiencing disregulated behaviours due to trauma and social anxiety. This leaves them in a distressed state that impacts on their readiness to learn. In addition we have two pupils who are Care Experienced that are under attaining for their age and stage due to low confidence and lack of enagement in learning at home.. Additional Pupil Support time is required to provide 1-1 and small group support to improve confidence, resilience and social skills in main group as well as support learning for 2 CE pupils. The school community is generally an affluent area but a small number of pupils experience relative poverty and the cost of the school day can have a negative impact on their learning experiences. |  |  |  |  |
| Expected Impact | Interventions Planned |  | Measure of Success (Triangulation of Evidence/QI Methodology) | Impact on learners Ongoing evaluation Dec/June |
| . Identified group of 8 pupils will have improved outcomes related to regulation and readiness to learn. 2 CE pupils will have increased attainment and engagement in learning due to closing gaps in conceptual understanding in writing and numeracy and improved confidence. Idenfied pupils will be supported financially with trips and resources for school. | PSA 6 hours per week - £5101 Resources - £100 (Lego, board game) £200 - Daily check-ins for pupils where they will be supported with 5 Point Scale, Emotion Works Toolkit and nurturing approaches. - 3 inputs weekly for Kitbag, Lego Club and Socially Speaking board game. - 3 inputs weekly for CE pupils in writing and numeracy concepts - Financial support for idenfied pupils to reduce cost of the school day. |  | Measures will be built into LS and tracking meetings for identified pupils HT meetings with Pupil Support Staff will take place to evaluate interventions termly and identify next steps. |  |