Tulliallan PS: Golden Jubilee Planning Group

| Date of meeting: | Monday 31st March 2025 |
| --- | --- |
| Present: | Donald Campbell (Community Council), Willie Anderson (History Society), Evie, Harrison, Poppy, Hana, Maisie, Cara, Odette, Nicola Davidson (parent), Jane Turnbull (Community Council), Nicola Bow (Headteacher) |
| Apologies | Sandra Burt (Community Council), Darren Empson (BBS and Gala Committee) |

| Minutes of meeting |  |  |
| --- | --- | --- |
| Area discussed | Main points | Actions |
| Welcome and introductions | N Bow welcomed everyone to Tulliallan and gave some background information about the school |  |
| Purpose of Group | - To plan Golden Jubilee celebration and make arrangements in the lead-up to the day. - Build community partnerships & involvement |  |
| Plans to date | - Date of celebration day: Friday 26th September - Celebration day will take the form of an Open Doors with planned events from 10/11am to approx. 6pm (times tbc) for families, community and ex-pupils and staff - Focus in term 3 has been on heritage (gathering stories and photos from the village’s past over the past five decades) - Focus in term 4 will be on legacy and making a mark as members of the community. Each class will focus on an area of the playground to develop - August learning in school will focus on history of the village (beyond the last five decades), using photos and stories as a stimulus |  |
| Celebration Day | - Discussed format of the day. Suggestions: 10/11am until 6pm; museum, art gallery, special lunch, music, Tasty Treats - Guest list has been created, details of event to be shared by planning group on social media - Commemorative logo and items have been commissioned. Tote bags, teddies, mugs and coasters have been ordered and will be available at school events in the lead up to 26th September. - Family lunch options to be explored. Think about outdoor shelter and options to include families - Discussed possibility of Kincardine pipe band and BBs performing at celebration event | - Names for guest list to be emailed to tulliallanps.enquiries@fife.gov.uk - Save the date poster to be sent to planning group and shared on social media - Commemorative items to be advertised to families, community, local businesses by all planning group members (share on Family Council, Kincardine community group, Kincardine legends, in community centre. Library, local businesses) - N Bow to contact school cook to see if special family lunch could be arranged for 26th September - Jane to contact local pipe band - Evie to contact BBs re performance on 26th September - N Bow to contact gala committee to see if marquees could be borrowed and set up for family lunch |
| Museum | - School lost photo archive when we had a fire in 2010. Willie and Donald have access to a large selection of photos and will arrange to copy some of them and create a display that can be used during the celebration event. - Fife Archive and land registry would provide useful sources of information – contact them to access maps and building plans and track changes in school building over time | - Donald to put request on community groups for photos and stories - School to contact land registry and Fife archive |
| Date of next meeting | Wednesday 7th May, 1.35pm at Tulliallan PS |  |