School Improvement Planning Template (Year 1: 2026 - 2027)

Progress			 Wellbeing			 Inclusion

| School | Annette Street PS |
| --- | --- |
| Learning Community | Shawlands LC |
| Link Officer | Michelle Wright |
| Head of Service | Carolyn Davren |
| School Roll | 195 |
| Attendance Rate | 82% |
| Pupils affected by the poverty related attainment gap (employment, income, housing, health, access to services, education, crime), covid & other forms of poverty not listed OTHER – Pupils not in SIMD 1 & 2, not in receipt of school meals but affected by factors detailed above. |  |
| PEF allocation 26-27: 89,000; SIMD Quintile 1 (% and Number) 73.4% 141 children. PEF Carry Forward: -£1000; SIMD Quintile 5 (% and Number) 0. Total PEF Allocation 26-27:89,000; Other 26.6%. FME (number and %) 36.1% 68 children; Total No Pupils 191. |
| Grand Challenges over 3-year cycle (Aug 2026 – Jun 2029) (Throughout the current 3 year cycle of improvement all establishments should focus on the Grand Challenges of Progress, Wellbeing and Inclusion) Progress: Establish consistent high-quality learning, teaching and curriculum pathways across the school, effectively capturing the progress of learners over time. Inclusion: Create consistent inclusive environments and strengthen relationships across the school community to ensure we are meeting the needs of all learners. Wellbeing: Embed our relationships policy to ensure we have nurturing, values led approaches and improved wellbeing across a rights respecting Gold School. |  |

| Challenge: Progress Overall Lead – Leslie Dougan |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Mission: To ensure best fit approaches to teaching reading are consistent across the school, leading to improved pupil attitudes to reading, teacher capabilities in teaching reading and improved attainment. |  |  |  |  | Costs |  |
| Commitments (sprints) | Outcomes | Measures of Impact | Lead Responsibility | Target Date | Core | PEF |
| 1. Establish a consistent whole-school approach to reading All staff will implement Thinking Reader, Guided Reading and explicit modelling approaches to ensure high-quality, consistent reading experiences across the school. | Staff will: - Implement Thinking Reader consistently. - Deliver Guided Reading at least three times weekly. - Explicitly model reading strategies and comprehension skills. - Use the Reading Progression Framework to plan learning and assessment. - Engage in moderation and professional dialogue to improve practice. Almost all learners will: - Apply a range of reading strategies independently. - Discuss texts confidently. - Demonstrate increased engagement in reading. - Experience a consistent approach to reading. Most learners will: - Increased confidence and enjoyment in reading. - Improve comprehension and strategy use. - Make expected or better progress in reading. By June 2027: - Reading attainment in P1, P3 and P5 will increase by 10%. - 70% of learners will identify and use at least three reading strategies. - 80% of learners will report enjoying reading. | Professional Dialogue - Planning and moderation evidence implementation of agreed reading approaches. - Staff report increased confidence in reading pedagogy. - Forward planning demonstrates progression and consistency. Classroom Observation - Thinking Reader approaches evident across classes. - Explicit modelling observed consistently. - Guided Reading delivered regularly and effectively. Learner Conversations - Learners explain reading strategies confidently. - Learners discuss texts using appropriate vocabulary. - Learners report increased enjoyment of reading. Quantitative Data - 10% increase in reading attainment. - Increased strategy use across P1, P3 and P5. - Positive learner survey data regarding reading. | Leslie Dougan | June 2027 | £1000 Literacy resources and manipula-tives | £5000 readers £1700 Seesaw £100 Picture News £65000 PEF teacher release Leslie out of class to raise attainment P1, P3 and P5 £1000 Develop -mental PE to improve motor skills & later reading skills |
| 2. Develop high-quality reading environments and resources All staff will create reading-rich environments and provide access to high-quality, culturally responsive texts that promote reading for pleasure and learner engagement. | Staff will: - Implement Reading Environment Standards. - Provide engaging and culturally responsive texts. - Promote reading for pleasure. - Ensure texts reflect the languages, cultures and experiences of learners. - Review and refresh resources regularly. Almost all learners will: - Access texts that interest them. - See themselves reflected in reading materials. - Read independently and for enjoyment. - Engage positively with reading environments. Most learners will: - Select texts independently. - Read more frequently. - Demonstrate positive attitudes towards reading. By June 2027: - 85% of learners will report they can find books that interest them. - 90% of learners will report reading materials are relevant and engaging. | Professional Dialogue - Staff demonstrate confidence selecting high-quality texts. - Planning evidences purposeful use of reading resources. Classroom Observation - Reading environments meet agreed standards. - High-quality texts are visible and accessible. - Reading for pleasure is actively promoted. Learner Conversations - Learners discuss books they enjoy. - Learners report positive reading experiences. Quantitative and Perceptual Data - 85% positive responses regarding access to books. - 90% positive responses regarding relevance of texts. - Positive family feedback regarding reading resources. |  |  |  |  |
| Dec/May Evaluative Comments on impact of SIP work: (Used to support completion of SER) |  |  |  |  |  |  |  | Learner surveys; reading conversations; focus groups |

| Grand Challenge: Wellbeing Overall Lead – Jem Anderson |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Mission: To improve rights, relationships, play and participation, leading to improved wellbeing of all children |  |  | QI (HGIOS 4) |  | Costs |  |
| Commitments (sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility | Target Date | Core | PEF |
| 1. Embed the Behaviour and Relationships Policy All staff will implement the Behaviour and Relationships Policy consistently through values-based, restorative, nurture-informed and trauma-informed approaches. 2. Achieve Rights Respecting Schools Gold Accreditation All staff will embed children's rights across learning, teaching and school improvement to strengthen learner voice, participation and wellbeing. | Staff will: - Implement the policy consistently. - Use shared language linked to school values. - Apply restorative approaches effectively. - Use nurture-informed and trauma-informed practice. - Promote positive relationships and learner voice. Almost all learners will: - Feel safe, respected and included. - Demonstrate the school values. - Build positive relationships with adults and peers. - Identify trusted adults within school. Most learners will: - Demonstrate improved wellbeing and self-regulation. - Resolve conflict positively. - Participate confidently in learning. - Develop a stronger sense of belonging. By June 2027: - 85% of learners report feeling safe, respected and included. - 90% identify a trusted adult. - Recorded incidents requiring SLT intervention reduce by 10%. - 85% of learners can explain how school values influence behaviour and relationships. Staff will: - Explicitly reference rights in learning and teaching. - Use rights-based language consistently. - Embed rights within planning and school improvement. - Create meaningful opportunities for participation. - Use learner voice to inform decision-making. Almost all learners will: - Understand and articulate their rights. - Recognise how rights support wellbeing and learning. - Feel listened to and valued. - Participate in leadership and decision-making opportunities. Most learners will: - Demonstrate increased leadership and participation. - Use rights language confidently. - Contribute positively to school improvement. By February 2027: - Achieve Rights Respecting Schools Gold Accreditation. - 90% of learners can explain how rights influence learning and wellbeing. - 85% of learners report adults listen to and act upon their views. - 85% of families recognise the school's commitment to children's rights. | Professional Dialogue - Staff demonstrate confidence in restorative and relational approaches. - Consistency of language and expectations evident. Classroom Observation - Positive relationships evident across the school. - Consistent routines and expectations observed. - Restorative approaches used effectively. Learner Conversations - Learners explain school values confidently. - Learners describe how adults support them. - Learners report feeling safe and included. Quantitative and Perceptual Data - Reduction in behaviour incidents. - Positive learner wellbeing data. - Positive staff confidence measures. Professional Dialogue - Rights-based planning evident across the school. - Staff demonstrate confidence in rights-based practice. Classroom Observation - Rights visible in learning environments. - Rights-based language used consistently. - Learner participation evident. Learner Conversations - Learners explain their rights confidently. - Learners describe opportunities to influence change. Quantitative and Perceptual Data - Gold Accreditation achieved. - Positive learner and family survey data. | Jem Anderson Lee Ballantyne and Nicola Dineley | June 2027 | £1300 Wosdec training |  |
| Dec/May Evaluative Comments on impact of SIP work: (Used to support completion of SER) |  |  |  |  |  |  |

| Grand Challenge: Inclusion Overall Leads Wendy English and Heather Wallace |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mission: To ensure all learners, particularly those with EAL, ASN and additional wellbeing needs, can access, participate and achieve within environments that are consistent, welcoming, communication-friendly and responsive to individual needs. |  |  | QI (HGIOS 4) |  |  | Costs |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact |  | Lead Responsibility | Target Date | Core | PEF |
| 1. Establish Consistent Inclusive Learning Environments All staff will implement Inclusive Classroom Standards to create calm, predictable, communication-friendly environments that support participation, independence and achievement. | Staff will: - Implement Inclusive Classroom Standards consistently. - Use visual timetables and communication supports. - Establish consistent routines and expectations. - Apply inclusive, EAL-friendly and trauma-informed approaches. - Promote learner independence through accessible environments. Almost all learners will: - Feel safe, confident and ready to learn. - Access learning independently using visual supports. - Follow established routines and expectations. - Experience inclusive and welcoming environments. - Feel a strong sense of belonging. Most learners will: - Demonstrate increased independence. - Improve engagement and participation. - Regulate emotions more effectively. - Manage transitions successfully. - Sustain attention and readiness to learn. By June 2027: - 85% of learners report routines help them feel safe, confident and ready to learn. - 80% of P1, P3 and P5 learners demonstrate increased independence through visual supports and routines. - Recorded incidents relating to dysregulation, emotional distress and transition difficulties reduce by 20%. - Almost all learners experience consistent routines and expectations across the school. | Professional Dialogue - Staff demonstrate confidence in inclusive and EAL-friendly practice. - Classroom audits evidence implementation of agreed standards. - QA activities demonstrate consistency across classes. Classroom Observation - Visual supports evident in all classrooms. - Consistent routines and expectations observed. - Communication-friendly environments evident. - High levels of learner participation observed. Learner Conversations - Learners explain how routines and visual supports help them learn. - Learners report feeling safe, confident and included. - Learners describe strategies that help them manage transitions. Quantitative and Perceptual Data - 85% positive learner responses regarding routines. - 80% independence target achieved. - 20% reduction in dysregulation and transition incidents. - Positive family feedback regarding inclusion and accessibility. |  | Wendy, Heather, Cristina, Christina, Lucy | June 2027 | £1000 Resources And training | £1000 Resources |

| Grand Challenge | Area of Focus | QI HGIOS 4 |
| --- | --- | --- |
| Inclusion | Improve attendance and engagement. | 3.1, 3.2, 2.3 |
| Wellbeing | Families - Vision, values and aims embed Family support embed | 2.5 |
| Progress | Transition nursery to P1 – deepen multi-agency transition work | 2.7 |
| Progress | Learning routines e.g. LI and SC; further support with pedagogy wall | 2.3, 2.2 |
| Progess | Deepen use of Seesaw for assessment | 2.3, 3.2 |
| Wellbeing | Embed child protection best practice | 2.1 |
| Wellbeing | Embed Global Storylines | 2.2, 3.1 |
| Dec/May Evaluative Comments on impact of maintenance agenda work: (Used to support completion of SER) |  |  |

Maintenance Agenda:

Please use the space below to note any other improvement actions initiated in previous years which are continuing to be a focus in the coming year but not on your identified priority for 26-27

PPl