School Improvement Planning Template

| School | Barmulloch Primary School & ALN |
| --- | --- |
| Learning Community | Springburn |
| Link Officer | Louise Ballantyne |
| Head of Service | Jean Miller |
| School Roll | 106 (at Sept 24) |
| Attendance Rate | 94% (at Sept 24) |
| Pupils affected by the poverty related attainment gap (employment, income, housing, health, access to services, education, crime), covid & other forms of poverty not listed OTHER – Pupils not in SIMD 1 & 2, not in receipt of school meals but affected by factors detailed above. |  |
| PEF allocation 24-25: £61,250; SIMD Quintile 1 (% and Number): 47 (49.8%). Carry Forward: £19,025; SIMD Quintile 5 (% and Number): 5 (5.3%). Total Allocation 24-25: £80,500; Other: 11. FME (number and %): 54 (53%); Total No Pupils: 106. |
| Grand Challenges 2023-26 (Grand challenges are the long term strategic changes you intend to achieve i.e ‘to improve attainment in literacy) - Achievement and Progress: Improve pedagogy and assessment to increase attainment levels in Literacy - Engagement, Participation and Inclusion/Wellbeing and Learning: Embed inclusive practices throughout the school |  |

| Challenge 1: Achievement and Progress: Improve pedagogy and assessment to increase attainment levels in Literacy |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Mission 1: Improve pedagogy and assessment to increase attainment levels in Writing |  |  |  |  | Costs |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility | Target Date | Core | PEF |
| All staff to engage in professional learning with a focus on explicitly teaching writing (Stephen Graham/PM Writing), Literacy for All (LfA) approaches/trackers and reading into writing approaches. | All staff can apply explicit, LfA and reading into writing approaches. All staff can confidently use Literacy for All Frameworks and PM Writing resources for all learners in class. Almost all learners at P1,4 and 7 are on track with writing; 5% increase on 2024 ACEL data. | Professional dialogue Staff Surveys Tracking conversations | SLT/CLOL | Apr 24 |  |  |
| SLT, CLOL and P4 Teacher to engage in professional learning from CYPIC Wave 3 National Writing Programme and implement, track and report on improvements sharing learning with the wider staff team. | Almost all learners at P4 attaining expected outcomes by June 2025. All staff involved in the programme will report increased knowledge and understanding of quality improvement and effective writing approaches. | Professional dialogue Staff Surveys Tracking conversations Assessment activity and data analysis | SLT/CLOL/P4 Class Teacher | Jun 25 |  |  |
| P1-3 staff to develop use of Kaligo writing app and data to inform writing pedagogy. | All P1-3 staff are able to utilise data from app to inform pedagogy. Almost all learners have made good progress from previous levels. | Observations of learning Learner conversations and samples of work Tracking conversations | SLT/CLOL | Apr 24 |  | X – £1000 Kaligo licences/ styluses |
| Robust interrogation of writing assessment data by all staff through collaborative moderation leading to identified targeted writing groups as part of ‘fact, story, action’ tracking approach. | All staff able to quickly identify learners requiring targeted support. Almost all learners receive the support required to overcome barriers to learning in writing. | Observations of learning Learner conversations and samples of work Tracking conversations Assessment activity and data analysis. | SLT/CLOL | Jun 24 |  |  |
| Staff from P1-3 to continue developing Play Pedagogy approaches within writing with increased writing opportunities across the curriculum. | Almost all learners applying literacy learning through play experiences. All staff able to apply play pedagogy approaches to literacy experiences confidently. | Observations of learning Learner conversations and samples of work Tracking conversations Staff surveys | Play Pedagogy Lead /CLOL | Jun 24 |  | X - £400 GIC Play Pedagogy Programme |
| December Check Point: Evaluative Comments |  |  |  |  |  |  |

| Challenge: Achievement and Progress: Improve pedagogy and assessment to increase attainment levels in Literacy |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Mission 2: Establish Teacher Learning Communities to improve pedagogy with an initial focus on writing |  |  |  |  | Costs |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility | Target Date | Core | PEF |
| All staff to engage in professional learning on Teacher Learning Communities (TLCs) and their use in driving forward improvements in pedagogy. | All staff able to articulate the features of effective TLCs. All staff can apply key features of effective TLCs to their own TLC with a focus on pedagogy. | Staff surveys Professional Dialogue | SLT/Glasgow’s Pedagogy Champion | Dec 24 |  |  |
| All staff to work in newly established TLC’s to self-evaluate 5 key areas of effective Teaching and Learning and identify first focus area. | All staff are able to articulate whole school outcomes of self-evaluation against 5 key areas. All staff are aware of their own strengths and areas of development within the selected key area. | Professional Dialogue Staff Surveys Tracking Conversations | SLT/Glasgow’s Pedagogy Champion | Dec 24 |  |  |
| All staff to undertake professional learning in TLCs using Glasgow’s Pedagogy materials with a focus on area key area identified from self-evaluation. | All staff can identify the features of effective practice in identified key area. Almost all learners report improved experiences in class in identified key area. | Professional Dialogue Staff Surveys Tracking Conversations Observations of learning Learning Conversations | SLT/Glasgow’s Pedagogy Champion | Jun 25 |  |  |
| All staff to apply professional learning to writing lessons then extend to other areas once embedded using POLLI to evaluate progress. | Almost all staff observe almost all features of effective practice in key area. Almost all learners are engaged in learning within writing as a result of improved pedagogy. | Professional Dialogue Observations of learning Learning Conversations | SLT/Glasgow’s Pedagogy Champion | Jun 25 | X – cover for POLLIs |  |
| December Check Point: Evaluative Comments |  |  |  |  |  |  |
| Challenge 2: Engagement, Participation and Inclusion/Wellbeing and Learning: Embed inclusive practices throughout the school |  |  |  |  |  |  |
| Mission 1: Improve inclusive approaches through robust universal and targeted support |  |  |  |  | Costs |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility | Target Date | Core | PEF |
| All staff complete self-evaluation of inclusive approaches using CIRCLE Inclusive Classroom Scale and identify focus areas of development. | All staff aware of strengths and areas of development in inclusive approaches across the school. All staff able to articulate areas for development in own classroom practice. | CIRCLE Inclusive Classroom Scale Data Staff Surveys Learner Surveys | DHT | Oct 24 |  |  |
| All staff to self-evaluate approaches to promoting positive relationships leading to the creation of a consistent approach across the school with a focus on nurture. | All staff able to identify strengths and areas for development within relationships at Barmulloch. Almost all staff, learners and parents/carers report improved relationships across the school. | Staff Surveys Learner Surveys Wellbeing Web Data Learner Focus Groups Parent/Carer Surveys | PTs | Jun 25 |  |  |
| All staff to engage in professional learning focussing on the use of digital enhancements to support learners with an initial focus on writing. | All staff can articulate a range of digital tools available to support learners and can confidently utilise these as required. Almost all learners report improved use of digital tools to support learning. | Observations of learning Tracking Conversations Professional Dialogue Learner focus groups | DHT/DLOL | Jun 25 |  |  |
| Audit of whole school ASL with a specific focus on EAL, CEL, Neurodiverse learners and learners experiencing mental health challenges leading to identification of barriers and targeted additional supports required. | Update of ASL overview identifying barriers to learning and targeted strategies to support. All staff understand barriers to learning and consistently implement strategies to support learners to overcome these. | ASL Overview Data Wellbeing Web Data Staff surveys Learner Focus Groups | DHT | Jun 25 | x – £2704 counselling in schools budget | X - £21,113 Family Support Worker X - £29,000 SfLWs |
| December Check Point: Evaluative Comments |  |  |  |  |  |  |

| Grand Challenge | Area of Focus | Quality Indicator |
| --- | --- | --- |
| Engagement, Participation and Inclusion | Develop Rights Respecting School ethos leading to Silver accreditation. | 3.1 |
| Engagement, Participation and Inclusion | Improved communication and relationships with all stakeholders. | 3.1 |
| Achievement and Progress | Improve attainment in Numeracy using SEAL approaches. | 2.3 |

Please use the space below to note any other improvement action initiated in previous years which are continuing to be focus in the coming year but not your identified priority for 24-25.

PPl