School Improvement Planning Template (Year 1: 2026 - 2027)

Progress			 Wellbeing			 Inclusion

| School | Croftcroighn Primary & NC |
| --- | --- |
| Learning Community | Smithycroft |
| Link Officer | Anne Woods |
| Head of Service | Brian McDermott |
| School Roll | 62 primary & 5 nursery |
| Attendance Rate |  |
| Pupils affected by the poverty related attainment gap (employment, income, housing, health, access to services, education, crime), covid & other forms of poverty not listed OTHER – Pupils not in SIMD 1 & 2, not in receipt of school meals but affected by factors detailed above. |  |
| PEF allocation 26-27: £78,400; SIMD Quintile 1 (% and Number) 40.3% 27 pupils. PEF Carry Forward:; SIMD Quintile 5 (% and Number) 77.6% 52 pupils. Total PEF Allocation 26-27:; Other 3 addressed unrecognised for SIMD. FME (number and %) 67 pupils 100%; Total No Pupils 62 Primary & 5 Nursery. |
| Grand Challenges over 3 year cycle (Aug 2026 – Jun 2029) (Throughout the current 3 year cycle of improvement all establishments should focus on the Grand Challenges of Progress, Wellbeing and Inclusion) 1). Progress: Individual Progress. 2). Wellbeing: Relationships. 3). Inclusion: Inclusive Practice |  |

|  | Challenge: (copy/paste aligned challenge) 1). Progress: Individual Progress. To implement a system which enables clear tracking of individual learners’ progress over time through foundation & pre early levels into Early & beyond as appropriate. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mission : Individual children’s progress will be clearly recorded. |  |  |  |  |  | QI (HGIOS 4) QI 2.3 & 2.2 | Costs |
| Commitments(sprints) |  | Expected Outcomes | Measures of Impact | Lead Responsibility | Target Date | Core | PEF |
| Staff will explore different methods of tracking pupil progress. Staff will select & trial preferred methods of tracking ind. progress. |  | Almost all children’s progress will be clearly evidenced & tracked. | Individual tracking documentation | SLT Member | Dec2026 -start trial |  | £2000 |
| Staff will identify explore core curriculum resources to support children to make progress within early level CfE. |  | A few children will make more consistent progress. | Individual attainment for learners at early and first levels will be clearly evident in planning & tracking documentation. | SLT Member | Resources purchased by Nov & training comp. to impl. Jan |  | £2000 |
| Dec/May Evaluative Comments on impact of SIP work: (Used to support completion of SER) |  |  |  |  |  |  |  |

| Grand Challenge: (copy/paste aligned Grand Challenge from above) 2). Wellbeing: Relationships. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mission: (medium term strategic change achievable within an academic year) To build relationships with parents, campus partners & wider community to support our children’s learning. |  |  |  | QI (HGIOS 4) QI 2.7 & 2.5 |  | Costs |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility |  | Target Date | Core | PEF |
| Survey families to identify & plan a calendar of family learning opportunities. | Most children will be supported using similar strategies across home and school environments due to shared understanding & knowledge. | Increased parental involvement in family learning activities. Calendar of family learning events produced following feedback from parents. Increased attend. & feedback. | L. Harris M. Gartshore |  | Calendar of events planned by Nov. |  |  |
| Talk with campus partners to identify opportunities for joint campus child & family learning activities. | Most children &/or families will have opportunities to participate in joint campus learning opportunities. | Opportunities planned across the session for joint child & family learning. SLT tracking of engagement in joint learning opportunities. Feedback from children & families at/after events. | L. Harris M. Gartshore SLT Member |  | Initial calendar of events planned by Nov. |  |  |
| Dec/May Evaluative Comments on impact of SIP work: (Used to support completion of SER) |  |  |  |  |  |  |  |

| Grand Challenge: (copy/paste aligned Grand Challenge from above) Inclusion: Inclusive Practice. To increase the use of a range of Alternative & Augmentative Communication strategies across the school day to support engagement, participation and inclusion. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mission: (medium term strategic change achievable within an academic year) To further enhance our use Core boards, OOR, VOCA, Signalong to support communication throughout daily teaching/learning activities. |  |  |  | QI (HGIOS 4) QI 2.4 & 2.2 |  | Costs |  |
| Commitments(sprint) | Expected Outcomes | Measures of Impact | Lead Responsibility |  | Target Date | Core | PEF |
| All support staff will engage in Signalong training. | Almost all children will have access to staff who are skilled & confident in the use of Signalong across the school day. | Signalong Tutors will plan a series of training sessions for support staff. Support staff will complete a w/shop. All staff will increase their use of signing. Lesson observations, conversations with pupils. Feedback from staff & parents about signing. | E. Jamieson M. Gartshore Primary & D Morris Nursery |  | Start sep-26 |  |  |
| All curriculum lessons will have AAC supports available for staff to model throughout. | Almost all children will have access to appropriate AAC & staff who can confidently model this during lessons & learning activities. | Lesson observations will show that almost all teachers/CDO’s/support staff used AAC to support learners to communicate during lessons. | E. Jamieson M. Gartshore Primary & D Morris Nursery |  | June 27 |  |  |
| Staff will work collaboratively to identify agree common symbols, visual supports & OOR which can be used across the school – LCfE accreditation | Almost all children will have access to consistent visuals &/or OOR used across the school environment to support communication. | Almost all classes will display consistent commonly agreed symbols & visual supports or use of OOR. Progress towards LCfE accreditation. | E. Jamieson L. Harris V. Padden |  | June 27 |  |  |
| Staff will value & recognise the right of children to express their opinions. | Almost all children have opportunities to express their opinions across the school day. | Classroom observations will show that children have opportunities to express their opinions. Staff will identify meaningful opportunities to afford children ‘a voice’. A pupil council will rep. wider pupil body. l will be rep. pupil voice. | E. Jamieson |  | Oct 26 |  |  |
| Dec/May Evaluative Comments on impact of SIP work: (Used to support completion of SER) |  |  |  |  |  |  |  |

Maintenance Agenda:

Please use the space below to note any other improvement actions initiated in previous years which are continuing to be a focus in the coming year but not on your identified priority for 26-27

| Grand Challenge | Area of Focus | QI HGIOS 4 |
| --- | --- | --- |
| Wellbeing: Relationships | To continue to embed knowledge and understanding of nurture approaches to promote positive relationships & understanding of distressed behaviour by all staff. | QI 3.1 |
| Dec/May Evaluative Comments on impact of maintenance agenda work: (Used to support completion of SER) |  |  |

PPl