-

School Improvement Planning Template

|  |  |
| --- | --- |
| **School** | **Cuthbertson Primary** |
| **Learning Community** | **Shawlands** |
| **Link Officer** | **Michelle Wright** |
| **Head of Service** | **Donnie MacLeod** |
| **School Roll** | **360** |
| **Attendance Rate** | **86%** |
| **Pupils affected by the poverty related attainment gap (**employment,  income,  housing,  health,  access to services,  education, crime), covid & other forms of poverty not listed  **OTHER** – Pupils not in SIMD 1 & 2, not in receipt of school meals but affected by factors detailed above. | |
| |  |  |  |  | | --- | --- | --- | --- | | **PEF allocation 23-24:** | **112,000** | **SIMD Q**uintile 1 **(% and Number)** | **45%** | | **Carry Forward:** |  | **SIMD Q**uintile 5 **(% and Number)** | **1%** | | **Total Allocation 23-24:** | **112,000** | **Other** |  | | **FME (number and %)** | **35%** | **Total No Pupils** |  |   **Grand Challenges 2023-26 (***Grand challenges are the long term strategic changes you intend to achieve i.e ‘to improve attainment in literacy)* | |
| **Improving Attainment and Achievement**  **Developing our BGE** | |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Challenge:** | | | | | | |
| **Mission 1:** | | | | | **Costs** | |
| **Commitments(sprints)** | **Expected Outcomes** | **Measures of Impact** | **Lead Responsibility** | **Target Date** | Core | **PEF** |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Challenge: Improving Attainment and Achievement (Literacy/Numeracy)** | | | | | | |
| **Mission 1: Improve Reading and Writing Attainment** | | | | | **Costs** | |
| **Commitments(sprints)** | **Expected Outcomes** | **Measures of Impact** | **Lead Responsibility** | **Target Date** | Core | **PEF** |
| Targeted support groups for reading alongside team teaching | Increase reading age of targeted group beyond 12mths | Tracking and assessment data | PS/SM | June 24 | x | £30000 (0.5FTE) |
| Targeted support groups for writing alongside team teaching | Increase writing attainment by 2 levels (Ros Wilson criteria) | Tracking and assessment data | PS/SM | June 24 | x | £30000 (0.5FTE) |
| Class teacher to engage in LILT Effective Feedback training | Best practice agreed and consistent approach across school  Children understand current level and next steps | Learning Conversations  Planning Meetings  Classroom Observations | SH | June 24 | x |  |
| **Challenge: Improving Attainment and Achievement (Literacy/Numeracy) (contd)** | | | | | | |
| **Mission 2: Improve Attendance by 2%** | | | | | **Costs** | |
| **Commitments(sprints)** | **Expected Outcomes** | **Measures of Impact** | **Lead Responsibility** | **Target Date** | **Core** | **PEF** |
| Target families and learners in a variety of appropriate ways | Increase overall attendance by 1% 2023/24 and 1% 2024/25 | Attendance data | LM | June 24  June 25 | X |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
| Evaluative Comment (*HGIOS 4 Link Outcome to QI Challenge Questions)* | | | | | | |
| **Challenge: Developing our BGE** | | | | | | |
| **Mission 1: Refreshing our contexts for learning** | | | | | **Costs** | |
| **Commitments(sprints)** | **Expected Outcomes** | **Measures of Impact** | **Lead Responsibility** | **Target Date** | **Core** | **PEF** |
| Renew IDL contexts to reflect GCC frameworks | IDL contexts suited to school context and frameworks ensuring sufficient coverage and progression | Planning meetings/planning evidence | SM | June 24 | x |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
| **Challenge: Developing our BGE (contd)** | | | | | | |
| **Mission 2:**  Introduce vocational learning for P7 children | | | | | **Costs** | |
| **Commitments(sprints)** | **Expected Outcomes** | **Measures of Impact** | **Lead Responsibility** | **Target Date** | **Core** | **PEF** |
| Offer a variety of career/skill focused learning opportunities to P7 children | Increased engagement  Improved attendance  Improved aspirations | Learning Conversations  Individual attendance stats | SM | June 26 | x | £TBA |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
| Evaluative Comment (*HGIOS 4 Link Outcome to QI Challenge Questions)* | | | | | | |

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Challenge:** | | | | | | | | | | |
| **Mission 1:** | | | | | | | | **Costs** | | |
| **Commitments** | **Expected Outcomes** | | **Measures of Impact** | | **Lead Responsibility** | **Target Date** | | **Core** | **PEF** | |
|  |  | |  | |  |  | |  |  | |
|  |  | |  | |  |  | |  |  | |
|  |  | |  | |  |  | |  |  | |
| **Mission 2 :** | | | | | | | | | | |
| **Commitments** | | **Expected Outcomes** | **Measures of Impact** | **Lead Responsibility** | | | **Target Date** | **Core** | | **PEF** |
|  |  | |  | |  |  | |  |  | |
|  |  | |  | |  |  | |  |  | |
|  |  | |  | |  |  | |  |  | |
| **Evaluative Comment** *(HGIOS 4 measuring impact and progress)* | | | | | | | | | | |