## Sheet1
TASKS | 2016-08-22 | 2016-08-29 | 2016-09-05 | 2016-09-12 | 2016-09-19 | 2016-09-26 | 2016-10-03 | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28
Finalise presentation/resources for Inset, and deliver
Meet with PT to seek feedback/refine action plan
informal discussions with colleagues
Nurture Assessment tools purchased
Request for resources PTA
Initial request for identification of children
Teachers submit names
List compiled and inform parents of Assessment
initial assessment undertaken (Boxall)
Assessment overview meeting
analysis of existing data (CEM attendance etc.)
Decision meeting with teachers (Nooks Vs Nurture Group)
Inform parents
intervention initiated (Nooks or Group)
mid-point liaison and problem-solving
termly review
IAF Form 4 Targets
Project Team discussion/action planning
TIME (week commencing)