**All Saints Primary and Communication & Language Base**

**RECOVERY PLAN – JANUARY- JUNE 2021**

**PRIORITY 1: PLANNING FOR SOCIAL DISTANCING/HEALTH AND SAFETY**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Tasks / action** | **RAG of progress** | | **Who is responsible?** | **Timescales** | **Partners / LA Links** | **Resources / CLPL** |
| **Jan-March** | **April-June** |
| 1. Individual and school risk assessments to be reviewed and changes implemented to ensure continued health and safety of users. |  |  | DHT and all staff | January 2021 | Building Services  Health and Safety Team | Signage/  Cleaning materials |
| 1. Ongoing communication of Scottish Government advice and guidelines to all users. |  |  | HT  SLT  Class teachers | Ongoing | Building Services  Health and Safety Team | Risk Assessments |
| 1. Review and adapt school areas/classes for use as hub as appropriate. |  |  | HT and all staff | January 2021 | Building Services  Health and Safety Team |  |
| 1. Information shared with users for return from lockdown, hub use etc. |  |  | HT | Ongoing |  |  |

**PRIORITY 2: PLANNING FOR HEALTH AND WELLBEING**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Tasks / action** | **RAG of progress** | | **Who is responsible?** | **Timescales** | **Partners / LA Links** | **Resources / CLPL** |
| **Jan-March** | **April-June** |  |  |  |  |
| 1. Regular wellbeing check-ins with staff with offer of supervision/counselling approach sessions. |  |  | HT | January-June 2021 |  |  |
| 1. Curriculum planning to include daily focus on Health & Wellbeing throughout term. |  |  | SLT  Teachers | January-June 2021 | EPS  Active Schools  Barnados  Hive |  |
| 1. Staff training to support children’s wellbeing:  * Nurture Principles * Bereavement, Loss and Change * Trauma Informed Practices * PATHS * PPB |  |  | SLT and all staff | January-March 2021 | EPS  Attainment Challenge Team  Nurture Teacher  David Peden (Lomond View) | CLPL sessions in school |
| 1. Continued liaison with other professionals to support pupils and staff who are experiencing bereavement, anxiety or trauma. |  |  | SLT | January-June 2021 | EPS  ICOS  Barnardo’s  Action for Children  ASN Social Work |  |
| 1. Breakfast provision available to all pupils daily either in hub or school. |  |  | Breakfast Club Staff  Support Staff  Teaching Staff | January-June 2021 |  |  |
| 1. Provide, and encourage parents to include, regular, meaningful outdoor learning. |  |  | All staff  Parents | Ongoing |  |  |

**PRIORITY 3: PLANNING FOR EQUITY ISSUES/STRATEGIES FOR CLOSING THE GAP**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Tasks / action** | **RAG of progress** | | **Who is responsible?** | **Timescales** | **Partners /**  **LA Links** | **Resources / CLPL** |
| **Jan-March** | **April-June** |
| 1. Continued support to be targeted towards pupils who are disadvantaged during lockdown. |  |  | SLT  Class teachers/  Support for Learning staff | January-June 2021 |  | Literacy and Numeracy pathways |
| 1. Liaise with the local authority and other agencies to improve IT access for disadvantaged pupils. |  |  | SLT | January-June 2021 | Education HQ  Barnardo’s | IT equipment |
| 1. Additional support to be targeted towards pupils who have not engaged with remote learning – eg part time hub placements. |  |  | SLT  Class teachers/  Support staff | Ongoing |  |  |
| 1. Family Hub – HIVE – to continue to provide social, emotional support for families. |  |  | SLT  Janey McDonald, CLD Senior Worker (PEF)  Barnados | January-June 2021 |  |  |

**PRIORITY 4: PLANNING FOR CONTINUITY OF LEARNING**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Tasks / action** | **RAG of progress** | | **Who is responsible?** | **Timescales** | **Partners /**  **LA Links** | **Resources / CLPL** |
| **Jan-March** | **April-June** |
| 1. Audit of staff confidence in using ICT to support home/school learning.     Further training provided as needed. |  |  | SLT and ICT champion  CMO | January – June 2021 | Digital Literacy Officer | CLPL sessions in school or through Teams |
| 1. Moderation of remote learning – online learning and learning packs to ensure high quality teaching and learning which is meaningful, appropriate and progressive. |  |  | SLT | January-June 2021 |  |  |
| 1. Cluster planning and moderation of remote learning (online learning and learning packs). |  |  | SLT  Cluster SLT | February – June 2021 | Cluster  Attainment Challenge |  |
| 1. Development of Novel Studies planners across all levels. |  |  | SLT  Teachers within shielding category | Ongoing | Literacy CMO |  |
| 1. Introduction of Laudato Si (Change for Good) programme across the school – covers RE, Health and Wellbeing, Global Citizenship etc. |  |  | SLT | January – June 2021 | Scottish Catholic Education Service (SCES)  Paisley Diocese Primary RE Advisor | SCES Resources |