# Education – Improvement Planning Document – 2025-26

Establishment Name: Binnie Street Children’s Centre

CONTENTS

- Establishment Vision, Values and Aims

- 3 Year overview of priorities – based on the National Improvement Framework

- Action Plan for session 2025-26 including PEF planning

| Head of Establishment | Ruth Wyllie | Date | 14/6/2025 |
| --- | --- | --- | --- |

| Quality Improvement Officer |  | Date |  |
| --- | --- | --- | --- |

# Our Vision, Values and Aims

We value:

Honesty, Trust, Success, Friendship

Our Vision:

A happy friendly Centre with aspirations and expectations that all children will develop and learn in their own way.

Our Aims:

We aim to be approachable and transparent in our role as early educators and carers of children.

We will have aspirations for our children and encourage them to develop in their own individual way.

We aim to provide quality resources and experiences which support and challenge all our children

We aim to ensure that there is fairness and equity in everything that we do. We strive to give all our children and families the same opportunities to grow and develop.

We aim to encourage staff to continue to develop their skills and be enthusiastic about learning

We aim to engage with our local community and continue to value the strong nurturing relationships which we have developed over the years. .

# 3 Year Overview of Establishment Priorities

The improvement priorities for our establishment are noted on the following page. They have been expressed in the context of the National Improvement Framework

Our Improvement Priorities extend in a rolling programme over three years. Each priority has been coded accordingly:

Session 2025-2026

Session 2026-2027

Session 2027-2028

[

# Overview of rolling three year plan

| # National Priorities | Session 2025-2026 | Session 2026-2027 | Session 2027-2028 |
| --- | --- | --- | --- |
| Placing the human rights and needs of every child and young person at the centre of education | Promote numeracy and increase confidence in delivering an inclusive curriculum offer |  |  |
| Improvement in children and young people’s health and wellbeing | # Improved outcomes for our children to support a holistic child-centred approach to wellbeing and intervention |  |  |
| Closing the attainment gap between the most and least disadvantaged children and young people | To improve partnership with parents and families to create a strong supportive network around the child. |  |  |
| Improvement in skills and sustained, positive school-leaver destinations for all young people | # To improve outcomes to ensure children have the best possible start building lifelong learning, wellbeing and positive transitions |  |  |
| Improvement in achievement, particularly in literacy and numeracy | # To embed the numeracy strategy and continue to grow our numeracy and math support networks. |  |  |

# Stakeholder’s views

How were stakeholders views collected?

Views gathered through self-evaluation processes. Parents comments from information evenings, stay and play sessions, parent and child meetings Parents, staff and children’s questionnaires Verbal Feedback Twitter Professional Dialogue On line learning journals Sway Family Meetings

# Plan:  Session 2025-26

| Priority 1 Improvements in attainment, particularly in literacy and numeracy Closing the attainment gap between the most and least disadvantaged children and young people |  |
| --- | --- |
| National Improvement Framework Outcomes 4. High achievement and reduced attainment gap for all learners. 2. Strong partnerships between schools, services, families, and communities. 5. Skilled teachers and leaders delivering excellent, inclusive education. Education - achieving excellence and equity: National Improvement Framework 2025 |  |
| How Good is Our School/Quality Improvement Framework ELC 2.3 Learning, teaching and assessment 1.2 Staff skills, knowledge, values and deployment 3.2 Raising attainment and achievement 3.2 Raising attainment and achievement 2.5 Family learning 3.2 Securing Children's Progress | UNCRC Article 28: (Right to education): Article 3 (Best interests of the child): |

| Rationale for change based self-evaluation including data and stakeholder views |
| --- |
| To embed the numeracy strategy across our setting and continue to grow our numeracy and maths partnerships in order to provide consistency, share practice leading to improvements in learning and teaching. |
| Expected outcomes for learners Who? By how much? By when? What? |  |
| By October 2025 ,all staff will have an increased understanding of Inverclyde’s Numeracy Strategy which will strengthen practice to allow children to demonstrate their maths knowledge and skills in a range of ways and contexts. Almost all children will have developed their numeracy skills through a rich continuous provision. Provocations and learning experiences will be shared with all staff to ensure children are able to develop their numeracy skills indoors and outdoors. By May 2026, all staff will have access to ongoing, high quality professional learning that deepens their understanding of mathematical concepts and effective pedagogy. By May 2026 we will have developed successful partnership working with parents to support children’s numeracy development. We will have had a 50% increase in the number of parent workshops with a focus on how best to develop an understanding of the processes of maths and numeracy at a young age. By June 2026, On-going moderation with staff will have supported practitioner’s numeracy pedagogy and share best practice. By May 2026, we will have gathered data from using HIGIOUS’s self-evaluation toolkit ,auditing numeracy and maths provision within our (3-5 Room) This will give us a 70% increase in identified areas that require improvement. |  |

| Tasks to achieve priority | Timescale | RAG | Those involved/responsible – including partners | Resources and staff development |
| --- | --- | --- | --- | --- |
| Identify a Numeracy & Maths Champion | October 2025 |  | SMT Early Years Practitioners | Staff discussion at family meetings |
| Incorporate Family Learning Workshops into yearly curriculum overview | August 2025-June 2026 |  | SMT Early Years Teacher Numeracy & Maths Champion Location-OOSC -Room | Numeracy & Literacy Home learning Packs |
| Complete Numeracy Audit Toolkit (3-5 Room) | October 2025 |  | SMY Early Years Practitioners | Numeracy audit toolkit |
| Additional numeracy resources to be purchased | December 2025 |  | HOC-Budget Line. | Nursery Budget Line |
| Staff CPD Opportunities | August 2025-June 2026 In –Service Day Training |  | Early Years Teacher Ellis McAteer SMT | Seal Subitising |
| Weekly Maths Challenge (Parents & Children) | October 2025-July 2026 |  | Senior EYCO Numeracy & Maths Champion | Skills & Challenge questions to be devised. |

Measure of Impact: What we will see and where? How will we measure this? What does “better” look like? How will we recognise better when we see it?

Through monitoring the playroom using the self-evaluation audit tool we will be able to track improvements. We will be able to identify priorities and tasks and plan next steps. Through pre and post questionnaires we will be able to identify staff’s confidence when planning for a rich numeracy environment. Tracking and monitoring data will show targets and see if children making expected progress in numeracy. Staff will have increased confidence and be upskilled in delivering and facilitating very good numeracy experiences to all children. The Early years tracking tool kit will support staff and parents to see progression in children’s numeracy and plan for targets. We will measure this through playroom observations. We will observe an increase of environmental print within the playroom, numeracy resources and staff using mathematical language to support children’s understanding of numeracy across a range of contexts

| Priority 2 Improvements in attainment, particularly in literacy and numeracy Closing the attainment gap between the most and least disadvantaged children and young people |  |
| --- | --- |
| National Improvement Framework Outcomes 6. Positive relationships, behaviour, and attendance in a respectful culture. 2. Strong partnerships between schools, services, families, and communities. 4. High achievement and reduced attainment gap for all learners. Education - achieving excellence and equity: National Improvement Framework 2025 |  |
| How Good is Our School/Quality Improvement Framework ELC 2.5 Family learning 2.7 Partnerships 3.2 Securing Children's Progress 3.1 Ensuring wellbeing, equality and inclusion 1.3 Leadership of continuous improvement 1.3 Leadership of change | UNCRC Article 3 (Best interests of the child): Article 28: (Right to education): |

| Rationale for change based self-evaluation including data and stakeholder views |
| --- |
| Partnering with parents and families creates a strong, supportive network around the child, recognising and valuing diverse family structures, cultures and experiences ensures all children feel included and supported. Through a recent self-evaluation, informed by both quantitative and qualitative data we identified areas for improvement and a renewed focus on parental engagement. |
| Expected outcomes for learners Who? By how much? By when? What? |  |
| By October 2025 , all parents will complete Pre and post questionnaires to evaluate parental engagement. Evaluating parental engagement is a key component of nursery improvement. By January 2026 ,we would hope to see a 50% increase in parents participation when reading to their children for enjoyment through accessing weekly book bug sessions, our on line weekly bedtime story and nursery lending library. By December 2025 we will have established an active parents group who will actively supported establishment’s activities and events along with our nursery events team. By September 2025 we will have planned parent workshop in our curriculum overview. These will include numeracy and literacy workshops, cooking sessions and adult learning opportunities. By December 2025 ‘Engaging parents and families-A toolkit for practitioners ‘ –Education Scotland will be the supporting document that we will use over the course of the year to support parenting programmes and interventions and a family learning approach. By January 2026 a new family engagement policy will have been introduced that will include clear roles and responsibilities for involving families in the life of the centre .Our policy will highlight the challenges and barriers that may prevent parents from becoming involved in the wider life of the nursery and engage in their child’s own learning. This information will be collated through a range of methods such as face to face conversations, questionnaires or a parental needs analysis. |  |

| Tasks to achieve priority | Timescale | RAG | Those involved/responsible – including partners | Resources and staff development |
| --- | --- | --- | --- | --- |
| Pre & Post Questionnaires for parents around Partnership working from Nursery to Home? | October 2025 |  | SMT Parents | SMT to devise a Parental Involvement questionnaire-QR coded Education Scotland-‘Engaging parents & families-A toolkit for practitioners-Involving all parents’ |
| Identify key parents & staff for the implementation of a parents group. To develop our own family engagement policy. | December 2025 January 2026 |  | Parents Key staff SMT | SMT Parents & Staff |
| Plan dates in the diary over the year to support Parent Workshops to support Numeracy & Literacy | September 2025 |  | Early Years Teacher SMT & Staff | Overview of curriculum diary |
| Staff on rotation to read a weekly bedtime story to be shared on children’s individual learning journals. Out of school care children to read a chapter of chosen novel. | December 2025 |  | Staff Children | Establish location for the stories to be read. Digital resources to video and story stories. |
| Weekly book bug sessions to be held in Out of school care room | August 2025 |  | Staff SMT | Dates planned in diary Shared with parents in all comms |
| Re introduce children’s lending library with identified key staff | September 2025 |  | Key Staff | Reading Material Library bags |
| Maths problem of the week. A weekly skills challenge | October 2025-July 2026 |  | Megan-Maths Champion Louise –Senior EYCO | Maths resources |

Measure of Impact: What we will see and where? How will we measure this? What does “better” look like? How will we recognise better when we see it?

Evaluating the data from the early year’s tracker and children’s individual targets, we will see children making better progress in all areas of learning, especially in literacy, numeracy and health & wellbeing We will observe strong relationships between staff and our parents. Our families will gain ideas, resources and confidence to extend learning at home through every day activities. By evaluating the impact on a regular basis through self-evaluation it will allow us to measure the impact across our setting. We will see stronger home-nursery links which will contribute to improved literacy, numeracy and health & wellbeing outcomes for our children. We will see and hear children’s emotional wellbeing enhanced as our children will feel more secure and supported both at home and at nursery. We will observe through daily conversations and our on line journals parents being more confident and empowered to support their children’s learning From our family learning workshops our families are more likely to engage in learning activities at home when they understand the curriculum and given practical support Practitioners will be better supported to tailor individual learning experiences based from information from our families. This will correlate with our ‘All About Me’ booklet and our children’s individual personal plans

| Priority 3 Improvement in skills and sustained, positive school-leaver destinations for all young people Improvement in children and young people's health and wellbeing |  |
| --- | --- |
| National Improvement Framework Outcomes 3. Inclusive curriculum and assessment for a sustainable future. 1. Empowered and accountable education system supporting lifelong learning. 5. Skilled teachers and leaders delivering excellent, inclusive education. Education - achieving excellence and equity: National Improvement Framework 2025 |  |
| How Good is Our School/Quality Improvement Framework ELC 1.4 Leadership and management of staff/practitioners 1.1 Self-evaluation for self-improvement 1.3 Leadership of continuous improvement 4.4 Safeguarding and child protection 4.1 Nurturing care and support 3.1 Play and learning | UNCRC Article 2 (Non-discrimination): Article 3 (Best interests of the child): |

| Rationale for change based self-evaluation including data and stakeholder views |
| --- |
| Education Scotland & Care Inspectorate-‘A quality improvement framework for the early year learning and childcare sectors’, will provide us with a structured and consistent approach to evaluating and improving practice across all areas. It will help to identify strengths and areas of development ensuring all children regardless of background or ability receive equitable opportunities to thrive. |
| Expected outcomes for learners Who? By how much? By when? What? |  |
| - By December 2025 we will have started to gather data and evidence to evaluate our practice and improve outcomes for our children using the new quality framework. This will be used initially by SMT and then incorporated by staff. - By December 2025 a self-evaluation monitoring calendar will be in place to support the new framework. This will provide a record that self-evaluation has taken place. - By June 2026, we would see our children making measurable progress across key developmental areas. Interactions and activities will be better tailored to meet children’s individual needs and interest. - By June 2026, we will see staff working closely together to reflect, improve and share best practices through moderation within our centre and through cluster working. - Weekly family meetings with staff we can hear and see that staff understand their value and responsibility in the centre’s improvement through self-evaluation. |  |

| Tasks to achieve priority | Timescale | RAG | Those involved/responsible – including partners | Resources and staff development |
| --- | --- | --- | --- | --- |
| Staff to be given an overview of the new quality improvement framework. | October 2025 |  | SMT | October In-service day |
| A self-evaluation calendar will be in place to ensure all round monitoring within the centre is robust. | December 2025 |  | SMT |  |
| Updated paperwork /evidence will be in place to support the calendar and provide a record that self-evaluation has taken place. | December 2025 |  | SMT |  |

Measure of Impact: What we will see and where? How will we measure this? What does “better” look like? How will we recognise better when we see it?

- From the evidence and data that has been gathered we will we will see that rigorous self-evaluation is the responsibility of all practitioners and stake holders - An increase in staff’s confidence in evaluation specific areas of practice. All practitioners will understand that self –evaluation is an integral aspect of our approach to continuous improvement. - We will see an increase in stakeholder’s views and an inform change and improvement. - The self-evaluation calendar will ensure that there is a systemic approach to self-evaluation.