# Educational Psychology Service Improvement Plan (2025-26)

# Factors influencing the Improvement Plan

# The priorities of Inverclyde Educational Service Improvement Plan for 2023-24 will be:

# Contents

| Priority | Improvement Theme | lead | team | page |
| --- | --- | --- | --- | --- |
| - Service delivery | 1.a. Embedding systemic approaches within the team’s practice. | lisa | Daniela, Karen, Scott, John |  |
|  | 1.b. Quality improvement. | Jayne | Laurence |  |
| - Universal approaches | 2.a Enhancing Trauma responsive practices. | Lisa | Lisa & Erin |  |
|  | 2.b. Improving Attendance and Engagement. | Jayne | Attendance Lead, Aroojh |  |
|  | 2.c. Racial Equality and Anti-Racist Education | Scott | Aroojh |  |
|  | 2.d Improving pedagogy. | Taryn | Partners in education |  |
|  | 2.e Developing staff capacity to operationalize policy through practice | Jayne | Jayne Scott Taryn |  |
| - Targeted approaches | 3.a. Improving education experiences for Care Experienced CYP | Lisa | Partners in education & SW. |  |
|  | 3.b. Health and Wellbeing Hub | Laurence | Lisa, Erin & Scott |  |
|  | 3.c. Developing psych practice from the hub into lomond view. | Lisa | Lisa |  |

# Models for Improvement

This model is chosen due to its use across Inverclyde as a model for Improvement.  There will be some variation to the model Inverclyde practitioners often use ‘Assess, Plan, Do, Review’, in which the initial questions in the model are integrated into a wider holistic assessment.

# Service Improvement Plan Reviews.

## Rationale

To support our goal of delivering a high-quality, responsive service, we have established termly SIP review meetings. These meetings will help us maintain a sharper focus on our short-term objectives, while continuing to make progress towards the longer-term priorities set out in the Children’s Services Plan and the Education Service Plan.

## Role of Improvement groups

- Our team naturally adopts a distributive leadership approach, which has been further strengthened by recent Systemic Practices training. As a result, all EPs collaboratively share responsibility for working towards the termly SMART targets established during each SIP review.

- The role of the Leads is to have gathered information on progress of subgroups meeting SMART targets to share ahead and during SIP reviews.

## Features of SIP Review meetings.

- A shared discussion on what is working, what is a barrier and how to overcome this.

- A shared discussion as to the accuracy of impact data.

- The whole team should be involved in contributing to the process of Improvement Planning, measuring impact and feeding back.

- The quality improvement team will be collecting this data to inform the End of Year Report so standard support and challenge questions will be used.

## Aim of SIP Review meetings.

SIP Reviews will take place in an extended team meeting and will include time to review the previous term’s actions and identify the next set of actions.  In order for this to be most effective, it will depend on data being prepared ahead of the meeting by the subgroups.

| Cycle | SIP Review Dates |
| --- | --- |
| 1 | Wednesday 19th of November 2025 |
| 2 | Wednesday 22nd of April 2026 |
| 3 | Wednesday 17th of June 2026 |

These cycles will inform the following Quality Improvement Activities.

|  | When | Who |
| --- | --- | --- |
| Quality improvement data analysis | June 12th 2026 | QI team |
| End of Year Report | Deadline July 2026 | Jayne Johnson |
| SIP development day | June 17th and successive TMs | Whole Team |

| # Priority: Continuous improvement of service delivery ## 1.b Quality Improvement ## Aim: To evaluate our systems that improve processes, practices, and overall service delivery. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Learning from previous self evaluation. | Shorter term aim What are we trying to accomplish this year? | Long term aim How will we know a change is an improvement? ( 3 year change) | How will we do this? | Who is responsible? | Impact measures | RAG at Termly Planning Cycle Meetings. |
| - Piloting the termly 1:1 supervision enabled SMT to be more responsive to team/establishment needs. - A new model of QI was piloted (Data, Story, Action) that has been useful. - We learnt that developing educational staff capacity is easier to achieve at a school level than an authority level. - There is an increasing need to name our psychological input so that it is recognisable. | - Each member of staff to feel they are operating at their best and feel well supported. - Have a more robust analysis of training delivered as a whole service. - For staff to be confident in the psychology that they are offering and being able to name it. - For staff to feedback that the processes and procedures they use to deliver practice are effective. - Look for increased quantitative data to demonstrate the variety and range of EPS practice. - Look outward to other EPS’ to learn about what works. | - Increased consistency in EP practice. - Systems to continuously evolve to reflect community needs. | - Fully pilot the Data, Story, Action model 25-26. (see relevant doc for details) - Plan across the year the use of ASPEP’s self evaluation doc Jan 2024. - Implement the new methods to evaluate training. - Implement updated PLA processes - Gather establishment link feedback. - End yr report - Explore the use of Civica to determine if we can gather more accurate data collection (no of cases etc) - DHT meets with a regular group but will extend reach to other EPSs. | Jayne (and Laurence) MK JJ | - Data gathered from the ‘DSA’ process. - Data gathered from MS forms training. - Data gathered from stakeholder feedback. |  |

| # Priority: Learning and Teaching Aim: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Learning from previous self evaluation. | Shorter term aim What are we trying to accomplish this year? | Long term aim How will we know a change is an improvement? ( 3 year change) | How will we do this? | Who is responsible? | Impact measures | RAG at Termly Planning Cycle Meetings. |
| Metacognition in L&T has been cascaded Nationally within the SDEP conference and Universities. | By the end of this year, develop a feasible format for the distribution of knowledge to teachers across Inverclyde regarding skills to effectively integrate metacognition, cognition and self-study strategies into their teaching practice. EP will use link schools as a pilot. | Over the next three years, achieve sustainable integration of metacognitive, cognitive, and self-study skills into the teaching practices of educators across Inverclyde, resulting in improved student learning outcomes and teaching efficacy. | Continuous Professional Development: Offer ongoing CPD sessions to reinforce and expand teachers' understanding and application of metacognitive, cognitive, and self-study strategies. Resource Updates and Support: Regularly update resource packs and provide ongoing support through online platforms, peer networks, and EP consultations. Monitoring and Evaluation: Implement a robust monitoring and evaluation framework to track the programme’s impact on teaching practices and student outcomes, adjusting the approach as necessary. Stakeholder Engagement: Maintain active engagement with all stakeholders, including teachers, school leaders, parents, and students, to gather feedback and ensure the programme meets their needs. Reflective Practice and Collaboration: Foster a culture of reflective practice and collaboration among teachers, encouraging them to share experiences, challenges, and successes in applying the strategies. | Taryn | Teachers report increased confidence and competence in using the strategies, with average ratings above 4 on a 5-point Likert scale. A working format as informed by the pilot becomes a regular part of the professional development offerings for teachers in Inverclyde. High satisfaction rates from students, parents, and educational leaders, with at least 75% reporting positive impacts on student learning and engagement. |  |
| Raising the profile of Learning and Teaching as a core component of the EP role. | Within this year, establish a strong foundation for recognising and promoting Learning and Teaching as a core component of the Educational Psychologist (EP) role. | Over the next three years, embed Learning and Teaching as a recognised and integral part of the EP role, leading to enhanced educational outcomes and a broader understanding of EP contributions. | Raise awareness among stakeholders (e.g., school staff, parents, local authorities) about the importance of Learning and Teaching in the EP role. Organise workshops and seminars for EPs focused on Learning and Teaching strategies, enhancing their skills and knowledge in this area (see above). Implementation of Learning and Teaching within school case | All EPs | Percentage increase of stakeholders (e.g., teachers, parents, local authorities) who recognise Learning and Teaching as a core part of the EP role (as indicated in the number of Learning and Teaching cases) Increase in the number of EPs being asked to lead in Learning and Teaching professional development sessions. |  |

| # Priority: Provide CLPL to embed policy into practice Aim: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Learning from previous self evaluation. | Shorter term aim What are we trying to accomplish this year? | Long term aim How will we know a change is an improvement? ( 3 year change) | How will we do this? | Who is responsible? | Impact measures | RAG at Termly Planning Cycle Meetings. |
| We have evidence from previous year that authority wide training is not always practical for school staff, however we testing this further by ensuring that communication of the courses is more effective. | Embed practices that are key to the implementation of the PRP (2023). | Solution orientated,restorative practices and PPB remain key interventions in the authority and are embedded into systems. | Authority wide training offered on Restorative Practices, Solution orientated practices, PPB, and consultation at ASM Leads meeting. (see SO Programme of Development). | Scott Jayne John | - Evaluation forms. - ASN leads meeting - Feedback from EPs - ASG & ASN forum evidence of SO TACs. |  |
|  | Embed practices that are key to the implementation of the Anti-Bullying policy (2025). |  | Authority wide training is available on the policy as well as signposting. | Laurence (PEP) | - All schools will have a anti-bulling policy in line with Scot Gov recommendations. |  |

| # Priority: Attendance and engagement. Aim: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Learning from previous self evaluation. | Shorter term aim What are we trying to accomplish this year? | Long term aim How will we know a change is an improvement? ( 3 year change) | How will we do this? | Who is responsible? | Impact measures | RAG at Termly Planning Cycle Meetings. |
| Attendance Strategy is now outdated. | Embed the Attendance Policy into school practice. Stregthen the GIRFEC pathway to enhance partnership collaboration. | Have a more responsive GIRFEC pathway to support attendance and respond to non attendance. | Review the strands of the Attendance Strategy and update. Gather a needs analysis of where schools are it with understanding and responding to attendance data. Prioritise correct Attendance coding. Ensuring that knew services are using attendance data as an impact measure. Offering PCP training to support guidance/ SMT with detailed, child centred planning. Support the running of the 4 weekly Attendance Review by evaluating the aims, purpose and impact so far. | Attendance Lead and Depute EP. Linking with other key people. | - Evaluation forms. - ASN leads meeting - Feedback from EPs - ASG & ASN forum evidence of SO TACs. - Attendance dash board/data |  |

| # Priority: Expanding Implementation of Systemic Practices across the IEPS Aim: Develop EP Systemic Practices and Support across Case Work, School Improvement and Service Development |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Learning from previous self-evaluation | Shorter term aim What are we trying to accomplish this year? | Long term aim How will we know a change is an improvement? (3 year change) | How will we do this? | Who is responsible? | Impact measures | RAG at Termly Planning Cycle Meetings. |
| IEPS members have a range of intermediate, foundation and introductory skills in Systemic Practices Evaluation shows the impact and viability of Systemic Practices in EP work There is SLT, and team buy-in as well as support systems in place (i.e. triads) Previous triads and RTs has improved reflective practice within our team | Improved EPs skill in supporting CYPF through SP Increased collaboration working with CYPF and partner agencies Positive impact on schools and CYP | EPs show strength in systemic practice Improved relationships and reflective collaboration with partners Positive impact on educational and wellbeing outcomes (attendance and engagement, wellbeing, achievement) | Deliver practical workshops on key areas of SP (dates arranged for academic year) Triads and reflective teams support implementation and learning of SP (dates for these have been arranged for the academic year ahead) EPs conduct tests of change with new SPs Triangulate with historical and case-matched case work data to compare impact – identify benefits and limitations | Scott, Lisa, John | - Practice measures - Case studies - PLAs - Incidental data from working with CYPF - Incidental data from establishments and partners - Triad and reflective team discussion feedback |  |

| # Priority: Inclusion and Equity Aim: Improve anti-racist practice of Education staff through the development and delivery of psychologically-inform approaches across the Currie functions |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Learning from previous self evaluation | Shorter term aim What are we trying to accomplish this year? | Long term aim How will we know a change is an improvement? (3 year change) | How will we do this? | Who is responsible? | Impact measures | RAG at Termly Planning Cycle Meetings. |
| Involvement of EPS in teacher CLPL at the Equalities Coordinator Network (ECN) has improved staff knowledge and confidence, information gathering from pupils and communities and supported self-evaluation (ECN Evaluation) National level developments in anti-racist practice include psychological elements but is not explicitly psychologically-informed While schools are developing anti-racist practices, the EPS is progressing towards requirements to meet HCPC standards on equality - section 5 | All Levels 1 - Identify and integrate psychology into anti-racist education Service 2 - All staff will have improved knowledge and confidence in recognising the impact of their practice on culture, equality and diversity Local 3 – Ensure anti-bullying policy is racially-informed 3.2- Inverclyde Teachers and EPs are in receipt of and apply psychologically-informed anti-racist education National 4 - Scottish Teachers and EPs are in receipt of and apply psychologically-informed anti-racist education | All Levels 1 - Ensure anti-racist practices are explicitly psychologically-informed Service 2 - All staff will maximise non-discriminatory practice and apply enhanced inclusive practice Local 3 - Improved recording and addressing of racially motived bullying incidences 3.2 - Inverclyde pupils, staff and parents from minority backgrounds feel more safe and included National 4 - Scottish pupils, staff and parents from minority backgrounds feel more safe and included | All Levels 1.1 - Identify and link key psychology to anti-racist practice and apply within practice Service 2.1 – Review of practice using EPS Self-evaluation framework (consultation, assessment and intervention) 2.2 - EPS team apply learning in practice Local 3.1 – Provide input to EPS on new anti-racist anti-bullying policy 3.2 – EPs support schools on development of their anti-racist anti-bullying policy National 4.1 - Consult with practice-leading EPS (Glasgow) and Education Scotland national lead on inclusion of key psychological theory within anti-racist education | 1.1 Aroojh, Laurence, Scott (All EPs) 2.1 Scott, Aroojh, 2.2 All EPS 3.1 Laurence, Scott, Aroojh 3.2 All EPs 4.1 - Aroojh, Laurence, Scott | 1.1 Consultation with Respect Me / EP feedback 2.1 EP feedback 2.2 SIP review / triad discussions 3.1 EP feedback 3.2 Establishment SMT feedback / policy acceptance rates by Inverclyde 4.1 Knowledge and understanding of EPs on national updates | 1.1 2.1 2.2 3.1 3.2 4.1 |