MORAY COUNCIL      SCHOOL:	Anderson’s Primary          SCHOOL IMPROVEMENT PLAN    2019-20

| School Vision/Values: To build a world of our own, a place for all to share. Underpinned by sustainability, human rights, a strong sense of community and being aspirational |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| School Priority 1: Improving classroom standards |  |  |  |  |  |
| NIF Priority: Improvement in attainment particularly in Literacy and Numeracy. Closing the attainment gap between the most and least disadvantaged children. |  |  | HGIOS?4 QI: 1.1, 1.2, 1.5, 2.2, 2.3, 2.4, 2.5, 2.7, 3.1, 3.2 |  |  |
| NIF Driver: Teacher professionalism, Assessment of Children’s progress |  |  | Moray Priority: Learning and Teaching, Raising Attainment and Achievement |  |  |
| Actions | Outcomes for learners | Timescales |  | Responsible | Measures of success |
| Numeracy: Familiarise staff with Numeracy passports. Inform and engage parents re passports. Whole school uses passports. Familiarise staff with Northern Alliance Num progression. Whole school uses NA Num progression. Familiarise P1 staff with SEAL Num training. P1 and P1/2 staff implement SEAL numeracy. Familiarise P6 and P7 with Number Talks. P6 and P7 teachers implement Number Talks Literacy: Extend cross stage paired reading Info sessions for parents re paired reading. Extend story/rhyme sacks and parent info sessions Engage with Emergent Literacy training Implement Emergent Literacy strategies Use in First Ministers Reading Challenge to further develop Higher Order Reading Strategies Use Moray Tracker in Literacy and Numeracy | 5% increased attainment in Num by June 2020 20% increase in home learning engagement in P1 and P2 Improvement in mental agility through challenge passport. Increased enthusiasm- learners can challenge themselves to progress faster. Children more aware of the next steps in their learning. Improvement in mental maths skills in P1 and P2 Improvement in mental maths skills in P6 and P7. 3% improved attainment in Lit by June 2020 Increased engagement with reading and fun through peer support. Increased home learning participation Better foundation to build lit skills both phonics and writing Children experience fun and challenging reading opportunity. Children use variety of strategies to aid comprehension. | June Dec Aug Aug ongoing Oct Nov ongoing Oct Nov ongoing Jan ongoing Feb June 2020 Feb June (2019 ongoing) Aug ongoing Sep ongoing Sep ongoing |  | SMT SMT All Staff SMT All Teaching Staff Mrs Tulloch P1 and P1/2 staff Miss Jardine P6 and P7 staff Mrs Oates, CTs SMT SMT SFL and P1 teachers SfL and P1 teachers All teachers QIO support, all staff, SMT oversee | ACEL data SFL data Pupil focus group Parent focus group Classroom visits SNSA Moray Tracker data Teacher assessments Teacher planning TPJ PC feedback Home learning questionnaire |
| Evidence to support reduced bureaucracy/workload of teachers: Standing item on staff meeting agenda, change to WTA, adapted planning documents |  |  |  |  |  |

| School Priority 2: Extend the Development of Learner Skills for Learning, Life and Work |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Nif Priority: Improvement in employability skills and sustained positive school leaver destinations for all young people. |  |  | HGIOS?4 QI: 1.2, 1.3, 2.2, 2.5, 2.6, 2.7, 3.1, 3.2, 3.3 |  |  |
| Nif Driver: School Leadership, Parental Engagement |  |  | Moray Priority: Leadership at all levels, Supporting Learners |  |  |
| Actions | Outcomes for learners | Timescales |  | Responsible | Measures of success |
| Further raise staff awareness of Career Education Standards Further raise awareness of Moray Skills Pathway with parents Increase use of digital communication to engage and involve families Include skills development in home learning activities All P5-7 classes use My world of Work prolife Further embed contact with all 8 sectors to ensure experiences and entitlements Raise profile of STEM Further embed the teaching of skills through all curricular areas Social Enterprise | Children more aware of possible career opportunities Children more aware of their skills development and what they need to improve Parents more able to engage in children’s skills development Children more engaged/involved in their learning Children experience all eight employments sectors Engaged in real life social context for enterprise | Nov ongoing Jan ongoing Jan ongoing Dec ongoing Aug ongoing Aug ongoing Aug ongoing Aug ongoing Aug ongoing |  | Miss Mackenzie, SMT Miss Mackenzie, SMT All staff All staff P5-7 staff CTs supported by Miss Mackenzie Mr Troon All staff TBC | Classroom observations Displays Pupil focus groups Class teacher plans Parental focus group PC feedback Children’s annual report Teacher annual reports Moray Skills Pathway evidence file My World of Work profiles Social Enterprise outcomes |
| Evidence to support reduced bureaucracy/workload of teachers: standing item on staff meeting agenda, change to WTA, joined class working/events, better use of timetabled support staff, P5-7 online profiling. |  |  |  |  |  |

| School Priority 3: Relational School |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Nif Priority: Improvement in Children and Young People’s Health and Well-being. |  |  | HGIOS?4 QI: 1.3, 1.4, 2.1, 2.3, 2.4, 2.7, 3.1, 3.2 |  |  |
| Nif Driver: School Improvement, Performance Information. |  |  | Moray Priority: Curriculum, Self-Evaluation for Self-Improvement |  |  |
| Actions | Outcomes for learners | Timescales |  | Responsible | Measures of success |
| Renew curriculum rationale Formulate restorative policy Continue National Nurturing School programme: Further inform parents nurture principles Staff training on Zones of Regulation Staff training re restorative and solution orientated approaches Staff use restorative and solution orientated approaches Peer mediation training for staff Peer mediation training for children Peer mediation in place across school | More involved in their learning Children’s voice heard and they feel empowered Agreed restorative behaviour policy in place that they feel is fair, equitable and agreed by all. Improved behaviour leading to better learning Improved mental health and wellbeing Improved attainment | Sep – Jan Jan – April Aug ongoing Aug ongoing Sep –TBC Sep ongoing Sep ongoing Feb March ongoing |  | SMT PT All Staff PT Ed Psyc PT All staff DHT Support Staff TBC P6 and P7 | New curriculum rationale in place Restorative (behaviour) policy in place Community focus group Pupil focus group Cause for Concern tracker Tracking and monitoring meetings SFL data Classroom observations Boxall profiles Counsellor feedback Children’s reports PC feedback |
| Evidence to support reduced bureaucracy/workload of teachers: Standing item on staff meeting agenda, change to WTA, increased sharing of planning, ideas and resources. |  |  |  |  |  |