Moray Council PEF Pro forma:

| Academic Year | 2025-2026 |
| --- | --- |
| Name of School | Seafield PS |
| Amount of PEF | £58,800 |

| Data and Analysis (Baseline data) | PEF Priority Area | Proposed Intervention(s) to address your gap | Intended outcome and output | Measures: (…what ongoing information will demonstrate progress? Qualitative, Quantitative – short/medium/long term data) | Actual Impact |
| --- | --- | --- | --- | --- | --- |
| Local intelligence has been used and triangulated with SEEMiS data to highlight that food poverty and nurture needs area a presenting need. This is having an impact on pupils ability to listen, engage and participate in classroom learning which is contributing the PRAG. FSM data as well as packed lunch and snack audit has also informed this priority area. Data indicates that a significant number of FSM pupils are bringing in unhealthy packed lunches which are not nutritious. This is also creating financial pressures at home. The data suggests that 20 pupils will initially be targeted. This approach is supported by the children service plan that 8% of children in Moray are coming to school hungry. 30 families have self-reported that they are struggling to manage day to day routines, behaviour, homework and are seeking support from school. | Health and wellbeing | The target cohort (30 pupils from across the school) will be invited and supported to participate in: Targeted breakfast Club –5 days weekly to offer soft start and ensure that food poverty is addressed. As part of this intervention community larder food packs packs will be offered to identified families. This is in collaboration with the local co-op who will provide free, nutritious food to identified families via the freezers and fridges in the HSLW area. Establish a daily healthy tuck shop for all pupils to access. A home school link worker will support families and pupils to increase Free School Meals uptake and reduce Packed Lunch; this will be achieved 1:1 support to explore the issues and blockages of pupils accessing FSM in school. A home school link worker will offer weekly support to families and children to offer holistic support such as Seasons for Growth, Seafield Salon, Circle of Friends, check ins, referrals, support with benefits Home school Link Worker will support targeted families with budgeting and cookery of basic recipes with cheaper ingredients. | By October 2025, 100% of identified pupils will have access to a healthy breakfast club and nutritional food (from a baseline of 85%) All identified children will have access to an appropriate snack By December 2025, 15 of the identified cohort will access healthy and free school lunches (from a baseline of 10). By June2026 five families will have daily access to healthy microwave ready meals from school canteen (from a baseline of 0). By June 2025, 30 families will highlight improvements in behaviour at home and school Home-school link worker has regular checks ins with families and helps access benefits and local agency supports e.g. Bosie Home School Link Worker support 5 families with recipe cards and basic cookery skills to use cheaper ingredients | Registers kept and check ins with HSLW at breakfast club will demonstrate more children will have a breakfast Children will have access to a fruit/vegetable snack at break time – track children who regularly use this service via run charts Kitchen records to monitor FSM uptake. SEEMiS pastoral notes will be tracked to view if behaviour, participation and engagement has increased/decreased. GMWP will be used to track affiliation. Pre and post assessments will take place. Dental health will show signs of improvement in almost all pupils who attend (see individual charts and records) Qualitative feedback from parents and pupils will be sought via a verbal feedback and anonymous survey using Microsoft Forms. If appropriate, a case study will be developed from this feedback. Pastoral notes are used to record meetings with parents Recipe cards shared with families and feedback given that they are used. |  |
| 70 children on the role are in child planning. Support is needed for targeted interventions | Health and wellbeing | Allocate PEF PSA 0.4fte to work with targeted pupils, in order to improve health and wellbeing, equity and inclusion. This also allows for another PSA to target children with phonics interventions in P4 upwards | 12 children each term have access to targeted support by a PSA for phonics interventions 9 children with exceptional needs will be supported through the use of Teachh trays and learning stations 9 children will have all their basic needs met that require support such as eating and toileting | School assessment information will be used to monitor progress. This includes interrogating prediction of a level data, three times a year. This coupled with monthly classroom observations and feedback will be used to inform if the interventions will be adopted, abandoned, adjusted or amplified. ACEL data will be used to evidence progress made by identified children. This will take place at the end of term 4. Qualitative feedback from pupils and parents will be captured pre and post intervention to evidence impact. |  |
| Local intelligence, data FSM data, CP data, pastoral and behavioural notes as well as data from GMWP and class room observations has indicated that a wellbeing approach is required to improve 30 pupils mental and emotional wellbeing. | Health and wellbeing | An Outdoor Nurture Teacher (0.2fte)and Pupil Support Worker (0.6 fte) will support targeted pupils via small groups and 1:1 support on a weekly basis. Therapeutic and risky play will form part of this approach. Inclusive Play will be explored with 12 pupils. This is to ensure that the playground is a safe and welcoming space for all which may reduce playground incidents. Seasons for Growth Programme will be targeted for 40 pupils from P2 – P7. | By June 2025, the identified pupils’ affiliation scores will have increased to 85% or above (from a baseline of 78%). By June 2025, the identified pupils autonomy scores will have increased to 85% or above (from a baseline of 78%). By July 2025, the identified cohorts V&A forms will have reduced to an average of 0.5 per month (from an average of 1.5 per pupil per month). | Glasgow Motivational Wellbeing Profile will be undertaken with the identified cohort at the beginning of the intervention. This will be repeated monthly. Feedback from classroom teachers will be recorded monthly to capture participation and engagement levels. A spreadsheet will be developed to capture, monitor and interrogate V&A forms. This will help feed into topics that support staff can address in the outdoor nurture provision. Qualitative feedback will be requested from parents and carers. This will be requested, pre and post intervention. |  |
| Attendance and late coming data, CP data and SOS data and FSM data has been triangulated with feedback from classroom teachers and parents to inform this approach. 60 pupils have been identified as benefiting from a targeted approach to address late coming and wider support needs that are underpinned by poverty. | Health and wellbeing | Daily targeted 1:1 follow up for persistent late coming and low attendance for approx. 60 families. Co-ordination of weekly child planning and SOS meetings to targeted families to explore holistic family support on an as and when basis. | By July 2025, the identified cohorts late coming data will have improved to an average of 0.5 late comings per week (from an average baseline of 1.0 per week). | A run chart will be kept by admin staff to capture late coming. This will be compared to pre intervention run charts on a monthly basis. |  |
| Feedback from pupils and parents and data from COTSD suggested that not having access to appropriate school uniform is preventing children from attending school. Parents were reporting that they were unable to replace old and outgrown uniform, due to living in relative poverty. | Health and wellbeing | Uniform wardrobe will be offered free of charge in collaboration with Moray community foundation who leads the Moray school uniform bank. This will be located in reception where parents and pupils can help themselves to clothing that they need. | By June 2025, 100% of parents will report that uniform is no longer a barrier for their children accessing school (from a baseline of 99% of parents sampled). | Excel spreadsheets will be kept of ingoing and outgoing stocks which will evidence uptake. Pre and post intervention attendance data will be monitored which may evidence an increase in attendance of pupils who are experiencing poverty. Qualitative data will be collated from parents and pupils, to evidence the impact of this resource. If appropriate, a case study will be developed from this feedback. |  |

PEF Staffing 2023/24

- HSL – Jeannie McHugh

- Classroom Assistant – Mandy Donaldson (cover)

- Outdoor Nurture – Steve Pittam

- Clerical – Additional Hours (Kerry Stuart, Lesley MacLeod)

- PE Additional Day – Jade Inkson

PEF Staffing 2024/25

- HSL – Jeannie McHugh 31.25 hours

- PSA  – Donna Hyndman 15 hours

- Clerical – Nicola Munro tbc

- Outdoor Nurture Teacher – Steve Pittam 0.2fte

- PE Teacher Additional Day – Debs Gault 0.2fte (on 0.6fte contract DSM)

PEF Staffing 2025/26

- HSL – Jeannie McHugh 31.25 hours

- PSA  – Donna Hyndman 15 hours

- Clerical – Nicola Black

- Outdoor Nurture Teacher – Steve Pittam 0.2fte

- Outdoor Nurture Pupil Support Worker  – Steve Pittam 0.6fte

Sarah Elliot Notes – 29.05.24

- Glasgow Wellbeing Profile – Use to measure impact of Leadership, use smiley faces for pupil views

- 2024 – 25 – Glee Club Attendance Data – monitor Friday pms

- FSM – Carry this on with canteen

- Target groups of 15 – 30 pupils for targeted PEF work