Driving Equity and Excellence

Improvement Action Plan

Session 2025-26

| School: | St Teresa’s RC Primary School and Nursery Class |
| --- | --- |
| Cluster: | Taylor High School |
| Head Teacher: | Nicola Wood |

| Improvement Plan Summary |  |
| --- | --- |
| School Priority 1: Raising Attainment in Numeracy | By June 2026, we will improve numeracy attainment for learners at key stages (P1, P4, and P7) through a consistent, progressive approach to teaching numeracy, targeted support for identified pupils, and enhanced staff confidence in using high-impact pedagogies. This will benefit all learners, with a particular focus on those in SIMD quintiles 1 and 2 and those not currently on track to achieve expected levels. We aim to increase: - Primary 4 attainment from 68% to 72% - Primary 7 attainment from 66% to 70% |
| School Priority 2: Meeting Learners’ Needs | All identified learners, experience a nurturing, inclusive environment where their wellbeing needs are identified early and met effectively through coordinated planning and support, leading to improved attendance and engagement. |
| School Priority 3: Curriculum | All learners across all stages, from nursery to upper primary, experience a curriculum enriched with play, active learning, and opportunities to develop meta-skills, leading to increased self-efficacy, self-esteem, and engagement in learning |
| Nursery Class Priority: | Establishing a cohesive nursery team and embedding a values-driven, high-quality early learning environment through robust self-evaluation and refreshed structures |

Vision Statement

At St. Teresa’s RC Primary School and Nursery Class, we will provide a safe and nurturing environment where our children and families thrive and flourish in a community of love, faith and learning.

Aims

Where we will:

•	Create an environment where children and families are loved and valued; where children are recognised as individuals and encouraged to reach their potential using their unique God-given talents.

•	Provide high quality learning child centred experiences; supporting and challenging children in their learning.

•	In partnership with the parish of St. Teresa’s, create a community of faith, where children learn to know Jesus, grow in faith and love of others through shared experiences of prayer, liturgy and the sacraments.

•	Provide an open and welcoming ethos where families are empowered to enhance the work and life of the school.

•	Recognise the importance of and develop respect for different beliefs and cultures

•	Ensure a culture of continuous development; where we seek the opinions and talents of all stakeholders to drive forward change and improvement.

•	Encourage a sense of wonder and appreciation of the world we live in and a sense of responsibility for it.

Values

At St. Teresa’s RC Primary School and Nursery Class, we recognise the importance of the Gospel Values and Love in our lives; helping us to make good choices and be the best we can be. All rooted in love, the values we will use to guide our actions and relationships are Kindness, Compassion, Faith, Understanding, Gentleness, Truth, Forgiveness and Integrity.

Audit and Consultation

In arriving at our improvement priorities, the school has taken account of Education and Families’ priorities, an audit of the previous year’s improvement plan and engagement with parents/carers and learners.

Details of engagement (pupils, parents/carers, partners)

Family Questionnaire – April 2025

Children questionnaire – Session 2024/25

2025-26 Improvement Plan

| Priority 1: Long Term Outcome What do you hope to achieve? What is going to change? For whom? By how much? By When? |  | By June 2026, we will improve numeracy attainment for learners at key stages (P1, P4, and P7) through a consistent, progressive approach to teaching numeracy, targeted support for identified pupils, and enhanced staff confidence in using high-impact pedagogies. This will benefit all learners, with a particular focus on those in SIMD quintiles 1 and 2 and those not currently on track to achieve expected levels. We aim to increase: - Primary 4 attainment from 68% to 72% - Primary 7 attainment from 66% to 70% |
| --- | --- | --- |
| Person(s) Responsible Who will be leading the improvement? | Nicola Wood |  |

| (Please insert the relevant information below using the codes above) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| NIF Priority: 5 |  | NIF Driver: 2,3,6 |  |  |  |
| NLC Priority: 1,2 |  | - QI:1.1 – 1.3 2.3 3.2 |  |  |  |
| - PEF Intervention: 4,5,6,11 |  | Developing in Faith/UNCRC: 2 Article 28: Right to an education |  |  |  |
| If you used any aspect of your PEF fund to support this priority; please detail the expenditure here: 0.2 PEF allocated to additionality in teaching – matched by Local Authority – will be used to employ teacher who will oversee and deliver interventions to close the gap in literacy and numeracy |  |  |  |  |  |
| RATIONALE (WHY?) Why have you identified this as a priority? What data did you have to support this? Improving attainment in numeracy continues to be a key priority for our school as part of our commitment to excellence and equity. Analysis of current data shows that while attainment in Primary 1 is strong, a dip is evident by Primary 4 and Primary 7. This indicates a need to strengthen progression, consolidation, and consistency in learning and teaching across the school. By setting higher, yet realistic and evidence-informed targets, we aim to narrow the poverty-related attainment gap and ensure all learners are equipped with the numeracy skills needed for future learning, life, and work. This improvement priority aligns with the National Improvement Framework drivers of raising attainment and closing the attainment gap, and supports the expectations within HGIOS 4 for well-paced progression, effective assessment, and responsive pedagogy. |  |  |  |  |  |
| Resources: Please include costs and, where relevant, state where cost is being met from, specifically if using PEF. Please denote PEF/or colour code if preferred, to indicate where PEF spend aligns with targets. CLPL, Resources to support CPI, Additionality in staffing, Use of support staff to deliver small group interventions. |  |  |  |  |  |
| EXPECTED IMPACT (SHORT TERM TARGETS) | INTERVENTIONS/ACTIONS TO SUPPORT IMPROVEMENT: HOW? |  | HOW WILL YOU TRACK PROGRESS? MEASURES | EVALUATION CHECKPOINT 1 (Internal Process) | EVALUATION CHECKPOINT 2 (Internal Process) |
| What will be the benefit for learners (be specific)? | What are you going to do to make the change? What key actions are required? Consider links to the NIF Drivers. |  | What ongoing information will demonstrate progress? (Qualitative, Quantitative – short/medium/long term data) |  |  |
| Develop and Implement a Progressive Numeracy Framework | - Audit current planning and delivery across stages for consistency and progression. - Staff have knowledge and understanding of numeracy progression pathways - Introduce shared planning tools. |  | - A progressive numeracy framework is fully embedded across P1–P7 with staff using shared planning tools consistently. |  |  |
| Targeted Support for Identified Learners | - Use data to identify learners not on track (with focus on SIMD 1 & 2). - Deploy additional support via targeted interventions and catch-up programmes. - Engage families through numeracy workshops and home learning strategies |  | - Targeted learners in SIMD quintiles 1 & 2 show increased engagement and progress, measured through tracking tools and standardised assessments. - Numeracy attainment rises to: - 72% at Primary 4 (from 68%) - 70% at Primary 7 (from 66%) - Learners report increased confidence and enjoyment in numeracy through pupil feedback and surveys. |  |  |
| Build Staff Capacity with High-Impact Pedagogies – working with Local Authority LTA programme | - Provide professional learning focused on mastery approaches, numeracy-rich environments, and formative assessment. - Facilitate lesson studies, peer observations, and coaching opportunities. - Promote practitioner inquiry to reflect and refine approaches. |  | - Staff confidence in delivering numeracy increases (measured by pre/post CPD surveys and professional dialogue). - Professional Enquiry results |  |  |
| Monitor, Evaluate and Adapt Practice | - Track pupil progress using formative and summative data. - Hold regular attainment review meetings with stage partners and SLT. - Use learner voice and pupil work as evidence of effectiveness. |  | - TIM paperwork reflects professional dialogue, coaching and target setting |  |  |
| Final evaluation (for submission): |  |  |  |  |  |

| Priority 2: Long Term Outcome What do you hope to achieve? What is going to change? For whom? By how much? By When? |  | All identified learners, experience a nurturing, inclusive environment where their wellbeing needs are identified early and met effectively through coordinated planning and support, leading to improved attendance and engagement. |
| --- | --- | --- |
| Person(s) Responsible Who will be leading the improvement? | Amanda Kilpatrick |  |

| (Please insert the relevant information below using the codes above) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| NIF Priority: 1,2,4 |  | NIF Driver: 2,3,4 |  |  |  |
| NLC Priority: 3 |  | QI: 1.3, 3.1 |  |  |  |
| PEF Intervention: 2,5,6,11 |  | Developing in Faith/UNCRC: Articles 3,12,23,29 DiF 3,6 |  |  |  |
| If you used any aspect of your PEF fund to support this priority; please detail the expenditure here: Deploy 1 fte to assess, plan for and support identified children to access |  |  |  |  |  |
| RATIONALE (WHY?) Why have you identified this as a priority? What data did you have to support this? Our school community is committed to creating an inclusive, nurturing environment where every child feels safe, valued, and supported to achieve their full potential. Currently, 30 out of 215 pupils (approximately 14%) present as neurodiverse or have a formal diagnosis. This includes a range of needs such as ASD, ADHD, sensory processing differences, and social/emotional challenges. As the needs of our learners become increasingly complex, we must enhance inclusive practice across the whole school to ensure that every pupil receives the right support at the right time. This priority supports the national focus on inclusion, aligns with the principles of Getting it Right for Every Child (GIRFEC), and reflects our values of compassion and understanding. |  |  |  |  |  |
| Resources: Please include costs and, where relevant, state where cost is being met from, specifically if using PEF. Please denote PEF/or colour code if preferred, to indicate where PEF spend aligns with targets. Additionality in staffing 1FTE financed through PEF and Local authority. Time ringfenced to support collegiate activities. The Circle Document, NAIT, SCERT materials, Support from Educational Psychologist. |  |  |  |  |  |
| EXPECTED IMPACT (SHORT TERM TARGETS) | INTERVENTIONS/ACTIONS TO SUPPORT IMPROVEMENT: HOW? |  | HOW WILL YOU TRACK PROGRESS? MEASURES | EVALUATION CHECKPOINT 1 (Internal Process) | EVALUATION CHECKPOINT 2 (Internal Process) |
| What will be the benefit for learners (be specific)? | What are you going to do to make the change? What key actions are required? Consider links to the NIF Drivers. |  | What ongoing information will demonstrate progress? (Qualitative, Quantitative – short/medium/long term data) |  |  |
| Staff confidence and competence in supporting neurodiverse learners will increase through professional development aligned with SCERTS and NAIT. | - Deliver SCERTS and NAIT training to all teaching and support staff. - Create learning communities for peer-to-peer knowledge sharing and problem-solving. - Monitor staff learning through reflective journals and coaching sessions |  | - Staff report a measurable increase in confidence and knowledge around inclusive practice (via pre/post surveys and professional dialogue). |  |  |
| A dedicated base classroom will be established to provide consistent, targeted support. | - Identify and resource a space for a nurturing, low-arousal classroom environment. - Develop a timetable and staffing model to support neurodiverse learners effectively. - Engage learners and families in shaping the use of the space. |  | - The base classroom is in use by targeted learners with positive feedback from pupils, parents/carers, and staff. |  |  |
| Neurodiverse learners will experience improved emotional regulation, higher engagement, and a stronger sense of belonging | - Effective and adaptive timetabling of Base Classroom to support learners across P1 – P4 - Effective use of support staff to ensure pupils have co-regulation supports |  | - Quantitative improvements in attendance and attainment (as previously specified). - Qualitative improvements in emotional regulation noted through behaviour logs, pupil narratives, and observation. |  |  |
| Leadership opportunities for neurodiverse pupils will be expanded to promote inclusion and pupil voice. | - Launch a pupil voice initiative specifically involving neurodiverse students. - Create leadership roles such as “Inclusion Ambassadors” or “Wellbeing Mentors.” - Offer training and recognition for all participating pupils. |  | - Neurodiverse pupils actively participate in leadership roles and report increased self-esteem and belonging. |  |  |
| All planning, assessment, and review meetings for pupils with additional support needs are scheduled, recorded, and actioned within agreed timescales to ensure timely and coordinated support reflecting updated GrfME tool. | - Develop and implement a staged intervention framework aligned with GIRFEC - Strengthen use of Child’s Plans and ensure regular multi-agency reviews |  | - 100% of identified pupils have up-to-date, reviewed plans - Reduction in absence rates; improved engagement data |  |  |
| Final evaluation (for submission): |  |  |  |  |  |

| Priority 3: Long Term Outcome What do you hope to achieve? What is going to change? For whom? By how much? By When? |  | All learners across all stages, from nursery to upper primary, experience a curriculum enriched with play, active learning, and opportunities to develop meta-skills, leading to increased self-efficacy, self-esteem, and engagement in learning |
| --- | --- | --- |
| Person(s) Responsible Who will be leading the improvement? | Sophie Miller Lauren O’Kane Tina Pickering |  |

| (Please insert the relevant information below using the codes above) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| NIF Priority: 3,4 |  | NIF Driver: 2,4 |  |  |  |
| NLC Priority:1,2,4 |  | QI:2.2, 2.3, 3.2 |  |  |  |
| PEF Intervention: 4,5,11 |  | UNCRC: Article 28, 31 DiF 2,6 |  |  |  |
| If you used any aspect of your PEF fund to support this priority; please detail the expenditure here: |  |  |  |  |  |
| RATIONALE (WHY?) Why have you identified this as priority? What data did you have to support this? Fostering a learning environment that values play, active engagement, and the development of meta-skills nurtures confident, motivated, and resilient learners. Embedding these approaches across the curriculum—beginning in the nursery class and building through primary stages—will promote self-efficacy and emotional wellbeing. Staff collaboration, CLPL, and PEF-supported strategies will drive this cultural and pedagogical shift. |  |  |  |  |  |
| Resources: Please include costs and, where relevant, state where cost is being met from, specifically if using PEF. Please denote PEF/or colour code if preferred, to indicate where PEF spend aligns with targets. Staff training, Ring fenced time for collegiate working, Resources to enhance play opportunities, participation in Cluster Improvement Pilot for Active Literacy |  |  |  |  |  |
| EXPECTED IMPACT (SHORT TERM TARGETS) | INTERVENTIONS/ACTIONS TO SUPPORT IMPROVEMENT: HOW? |  | HOW WILL YOU TRACK PROGRESS? MEASURES | EVALUATION CHECKPOINT 1 (Internal Process) | EVALUATION CHECKPOINT 2 (Internal Process) |
| What will be the benefit for learners (be specific)? | What are you going to do to make the change? What key actions are required? Consider links to the NIF Drivers. |  | What ongoing information will demonstrate progress? (Qualitative, Quantitative – short/medium/long term data) |  |  |
| 90% of teaching staff report increased confidence in delivering play-based and active learning through CLPL and peer collaboration. | Member of staff to engage in CLPL to develop knowledge and understanding of meta-skills. Working party for Play and meta-skills Working party to cascade learning to staff – Nov Inset |  | Staff questionnaire Learning walks Professional Enquiry |  |  |
| Pupil engagement and wellbeing scores (GMWP) show improvement, particularly in self-efficacy and emotional resilience | Meta-skills to be piloted as stand alone – delivered by trained staff. Participation in Pupil Leadership Groups |  | GMWP Assessment - termly |  |  |
| Pupil voice groups contribute to shaping learning environments and activities, with evidence of increased ownership and confidence in learning | Pupil Voice groups established for: Sport STEM UNCRC Digital Faith Laudato Si Timetabled opportunities for staff to lead groups. Establish journal books to record actions and impact. |  | Minutes from meeting. Evidence of work – consider floor books. Presentation of learning cascaded to school community |  |  |
| Play-based and active learning approaches are embedded in weekly planning across all stages, with clear links to curriculum outcomes and meta-skills development | Audit current planning and learning experiences to identify where play and active learning are already present and where gaps exist Deliver CLPL on play pedagogy, active learning strategies, and meta-skills (e.g. creativity, collaboration, resilience) Develop and share planning templates that explicitly link play/active learning to curriculum outcomes and meta-skills Facilitate stage-level planning sessions to co-design play-based and active learning experiences across the curriculum Introduce a whole-school progression framework for meta-skills and integrate it into planning and assessment Conduct learning walks and peer observations focused on play and active learning Gather pupil voice on learning experiences and sense of self-efficacy Review and refine planning practices based on feedback and evidence of impact |  | Audit completed; baseline established for each stage 90% staff report increased confidence in applying strategies Templates used consistently in termly planning Termly plans show increased use of active learning approaches Observations show increased learner engagement and use of strategies Pupil feedback reflects increased enjoyment and confidence |  |  |
| All staff will have greater confidence in delivering North Lanarkshire Active Literacy Programme | Continued engagement in CLPL for staff to familiarise self with current level of programme – relevant to class. SMT engage in focussed quality assurance practices to ensure consistent delivery across the school Staff will engage |  |  |  |  |
| Final evaluation (for submission): |  |  |  |  |  |

PEF ALLOCATION: £

nOrth Lanarkshire Council

Education & FAMILIES

EQUITY PLAN 2025-26

(Internal recording; random sampling of PEF/Equity Plans

will continue throughout the session).

| Rationale for EQUITY (PEF) plan |  |  |  |  |
| --- | --- | --- | --- | --- |
| Please provide below detail around your rationale for the Equity plan. Highlight how PEF expenditure is integrated to support improvement priorities. For priorities around equity please detail the poverty related gap which you are addressing and the data which supports your rationale. Consider the following: attainment, health & wellbeing, attendance, exclusion, participation, engagement. |  |  |  |  |
| Link to Improvement Plan | Detailed Costings | Priority/Description | Intended Outcome/Impact Please describe your planned use of SAC resource/PEF allocation and what you intend to achieve. | Evidence/Measures Please indicate what evidence you are going to collect to show impact and progression. |

Nursery Priority

### Rationale

Following recent staffing changes and structural adjustments, there is a need to:

- Build a shared understanding of high-quality early learning and care

- Embed consistent practice aligned with HGIOELC and Care Inspectorate Quality Framework

- Develop a nurturing, inclusive ethos rooted in Gospel values

- Ensure staff confidence in using new self-evaluation tools and QIs

### 🛠️ Key Actions

| Action | Lead | Timescale |
| --- | --- | --- |
| Facilitate team-building and vision-setting sessions rooted in Catholic ethos | HT/DHT | August–September |
| Introduce and unpack relevant QIs from HGIOELC and Care Standards | PT Early Years | September |
| Co-create new self-evaluation formats (e.g. reflective journals, learning walk templates) | Nursery Team | September–October |
| Establish regular team reflection slots (e.g. weekly huddles or monthly deep dives) | PT/Team | Ongoing |
| Align planning formats with refreshed structure and curriculum guidance | PT/Team | October |
| Gather baseline evidence of practice using new QIs | HT/PT | October–November |

### 📊 Success Criteria

- Staff can confidently articulate key QIs and how they apply to their practice

- New self-evaluation tools are used consistently and meaningfully

- Planning and pedagogy reflect shared values and curriculum guidance

- Team culture is collaborative, reflective, and child-centred

- Positive feedback from children, families, and external partners

### 🔍 Links to QIs

- 1.3 Leadership of change

- 2.3 Learning, teaching and assessment

- 3.1 Ensuring wellbeing, equality and inclusion

- 3.2 Securing children’s progress

Appendix 1:

When considering your School Improvement Priorities, you are asked to provide links to the following, as well as the Quality Indicators within HGIOS4 and HGIOELC:

| UNCRC | HGIOS 4 | National Improvement Framework |
| --- | --- | --- |
| Article 1 - definition of the child Article 2 - non-discrimination Article 3 - best interests of the child Article 4 - implementation of the Convention Article 5 - parental guidance and child's evolving capacities Article 6 - life, survival and development Article 7 - birth registration, name, nationality, care Article 8 - protection and preservation of identity Article 9 - separation from parents Article 10 - family reunification Article 11 - abduction and non-return of children Article 12 - respect for the views of the child Article 13 - freedom of expression Article 14 - freedom of thought, belief and religion Article 15 - freedom of association Article 16 - right to privacy Article 17 - access to information from the media Article 18 - parental responsibilities and state assistance Article 19 - protection from violence, abuse and neglect Article 20 - children unable to live with their family Article 21 – adoption Article 22 - refugee children Article 23 - children with a disability Article 24 - health and health services Article 25 - review of treatment in care Article 26 - social security Article 27 - adequate standard of living Article 28 - right to education Article 29 - goals of education Article 30 - children from minority or indigenous groups Article 31 - leisure, play and culture Article 32 - child labour Article 33 - drug abuse Article 34 -sexual exploitation Article 35 - abduction, sale and trafficking Article 36 - other forms of exploitation Article 37 - inhumane treatment and detention Article 38 - war and armed conflicts Article 39 - recovery from trauma and reintegration Article 40 - juvenile justice Article 41 - respect for higher national standards Article 42 - knowledge of rights Article 14 - freedom of thought, belief and religion Article 15 - freedom of association Article 16 - right to privacy Article 17 - access to information from the media Article 18 - parental responsibilities and state assistance | 1.1: Self-evaluation for self-improvement 1.2: Leadership for learning 1.3: Leadership of change 1.4: Leadership and management of staff 1.5: Management of resources to promote equity 2.1: Safeguarding and child protection 2.2: Curriculum 2.3: Learning teaching and assessment 2.4: Personalised support 2.5: Family learning 2.6: Transitions 2.7: Partnerships 3.1: Ensuring wellbeing, equality and inclusion 3.2: Raising attainment and achievement 3.3: Increasing creativity and employability PEF INTERVENTIONS - Early intervention and prevention - Social and emotional wellbeing - Promoting healthy lifestyles - Targeted approaches to literacy and numeracy - Promoting a high quality learning experience - Differentiated support - Using evidence and data - Employability and skills development - Engaging beyond the school - Partnership working - Professional learning and leadership - Research and evaluation to monitor impact EDUCATION AND FAMILIES’ PRIORITIES - Improvement in attainment, particularly literacy and numeracy - Closing the attainment gap between the most and least disadvantaged children - Improvement in children and young people’s health and wellbeing with a focus on mental health and wellbeing - Improvement in employability skills and sustained, positive school leaver destinations for all young people - Improved outcomes for vulnerable groups A QUALITY FRAMEWORK FOR ELC 1 Leadership 1.1 Leadership and management of staff and resources 1.2 Staff skills, knowledge, values and deployment 1.3 Leadership of continuous improvement 2 Children thrive and develop in quality spaces 2.1 Children experience high quality spaces 3 Children play and learn 3.1 Play and learning 3.2 Curriculum 3.2 Learning Teaching and Assessment 4 Children are supported to achieve 4.1 Nurturing care and support 4.2 Wellbeing, inclusion and equality 4.3 Children’s progress 4.4 Safeguarding and child protection | NIF Priorities - Placing the human rights and needs of every child and young person at the centre of education; - Improvement in children and young people’s health and wellbeing; - Closing the attainment gap between the most and least disadvantaged children and young people; - Improvement in skills and sustained, positive school leaver destinations for all young people ; - Improvement in attainment, particularly in literacy and numeracy. NIF Drivers - School and ELC Leadership - Teacher and Practitioner Professionalism - Parent/Carer Involvement and Engagement - Curriculum and Assessment - School and ELC Improvement - Performance Information NIF Outcomes - A globally respected, empowered, and responsive education system with clear accountability at every level that supports children, young people, and adult learners to thrive. The system enables the development of their knowledge, skills, values, and attributes that give them the best opportunity to succeed and contribute to Scotland’s society and economy. - Young people experiencing the benefit of schools and early years settings working in excellent partnerships with wider children’s services and other partners, families, and communities, in line with the GIRFEC approach. - Inclusive and relevant curriculum and assessment which gives young people the knowledge and skills necessary to contribute to society, and shape a sustainable future, while celebrating and supporting progression for all. - High levels of achievement across the curriculum for all learners, with action to close the poverty-related attainment gap - Highly skilled teachers and school-leaders driving excellent learning, teaching and assessment for all, especially those with additional support needs - Improving relationships and behaviour, and attendance, with increased engagement in learning and a culture of dignity and respect for all. - An education system engaging in digital technology to enhance all aspects of learning and teaching, supported by a digitally skilled workforce and tackling digital inequality. |
| Developing In Faith Roman Catholic Schools are required to provide links within their SIP and SIR to the themes contained within ‘Developing in Faith’, as requested by the Bishops’ Conference of Scotland. |  |  |
| 1. Honouring Jesus Christ as the Way, the Truth and the Life 2. Developing as a community of faith and learning 3. Promoting Gospel Values 4. Celebrating and Worshiping 6. Serving the common good. |  |  |