#### Eco-Schools Action Plan				Eyemouth Primary School						Updated: May ‘13

#### Eco-Schools Topic:   Litter							Date Range of this Plan:  2012-2013

# Our overall aims for this Topic are:

# maintain litter free school

# promote and encourage pupil understanding of littering

# encourage positive attitude to littering within wider community

| Action | Who's in charge? | When will it be done by? (if ongoing, when did it start?) | How can we monitor it? | How will we know when we're successful? | How much will it cost? | Did it work? Any ideas for the future? |
| --- | --- | --- | --- | --- | --- | --- |
| Maintain class litter picks | Litter Team | First phase completed by Dec ‘12 | Completed litter pick records | All classes involved Increased responsibility | 4p per printed page to inform classes Black bin bags = £12.29 for 200. | 18.12.12: Introduced to whole school. Lower classes engaged but upper classes not. > Litter team to visit classes on a weekly basis to remind / check-up. May ’13: All classes have ‘signed up’ to new rota. Still some inconsistency in completion. Lower classes better! |
| Re-establish links with St Abbs Marine Reserve to develop ‘adopt a beach’ scheme | Litter Team | First visit by Dec ‘12 | Completed marine reserve audits | Beach cleans added to school calendar. Beach litter reduced. | 4p per printed page to inform classes Black bin bags = £12.29 for 200. | 18.12.12: Had initial meeting with Georgia Connelly (St Abbs). > Agree dates and allocate pupils. May ’13: Had agreed to work with High School on joint beach clean but cancelled due to weather. Change of staff at St Abbs. Need to meet with new ranger. > Arrange new mtg and rota for classes. |
| Introduce ‘Keep Scotland Tidy’ community appeal | Litter Team SBC Environmental Services | Easter ‘13 | Volunteer record Litter pick records | Community working with school Community litter reduced | 4p per printed page to inform classes Black bin bags = £12.29 for 200. | 18.12.12: No action yet. May ’13: No action yet. > Make posters to put up around Eyemouth. > Arrange community litter pick. |

| Purchase new ‘character’ bins for playground | Litter Team | Easter ‘13 | Minutes of meetings | New bins in place in playground | TBC | 18.12.12: Initial research showed bins to be VERY expensive. SBC have offered us a novelty bin. May ’13: Offered bin never turned up ( > Eco member to phone SBC Central. |
| --- | --- | --- | --- | --- | --- | --- |