Education Resources

Curriculum and Quality Improvement Service

School Improvement Plan and Standards and Quality 2025/2026

Law Primary School & ELC

Strategic Improvement Priorities Plan over 3-year cycle

Timescale: 24/25-26/27

| Strategic Priority | Year 1 24/25 | Year 2 25/26 | Year 3 26/27 |
| --- | --- | --- | --- |
| 1. | Develop whole-school approaches to learning for sustainability through implementation of elements of curriculum map with focus on UNCRC rights, outdoor learning and sustainable development | Further develop learning for sustainability embedding all areas incl, global citizenship and implementing updated Making Rights Real across all staged | Self-evaluate any further areas for development and identify improvements needed with learning for sustainability |
| 2. | Develop STEM approaches with focus on Science skills and STEM challenges and context-based projects | Further develop STEM with focus on technologies and implementation of planning. Embed Science skills progression. | Further development of STEM with focus on digital literacy and computing science. Embed technologies progression. |
| 3. | (LC) Moderation of writing across Carluke LC | Further development of writing criteria to support writing moderation across LC | TBC |
| 4. |  | Implement a VCPA approach across the school to increase pupil confidence and begin to raise attainment in Numeracy. | Enhance curriculum planning and LTA in numeracy and maths to ensure regular, relevant opportunities for breadth, depth and application of learning. |

The following Strategic Priority has been moved to maintenance agenda:

| Strategic Priority | Year 1 24/25 | Year 2 25/26 | Year 3 26/27 |
| --- | --- | --- | --- |
|  | Develop skills for learning, life and work through inclusion of skills-based framework across all areas and all stages ELC to P7 with focus on adapting LI’s and SC, personal achievement and target setting in pilot stages | Further develop skills-based learning through online profiling across all stages | Embed skills-based learning within the four contexts for learning |

Law Primary School and ELC is a rural, non-denominational school in the Clydesdale area of South Lanarkshire, near the town of Carluke. It has approximately 277 pupils including 56 children accessing 1140 hours in our early learning and childcare service.  The 2024-2025 staff team consisted of a head teacher, acting depute head teacher, acting principal teacher, 12 permanent teaching staff, 1 NQT, 1 area cover teacher, 8 support assistants and 10 early years staff.  The local area is a mixture of social and privately-owned housing, with new housing currently being built.  Local amenities and transport links are poor however there is an active community council which organise local events throughout the year.  Opportunities for local employment are limited however there are a range of employers in Carluke and other surrounding towns.

The school building opened in June 2006 and provides a modern campus for children to learn and achieve.  There continues to be improvements made to the aesthetics of the inside of the building including new floor coverings and painting to create an inspiring learning environment.  We have a large outdoor environment to enhance and extend learning including an orchard, trim trail, potting shed, polytunnel, outdoor classroom, wooded area, gardens and Secret Garden as well as a multi-use pitch. All classes have access to C-Touch interactive boards, a set of chromebooks, and a set of ipads or tablets allowing pupils to shar devices, one-between-two across the school.

Law Primary School & ELC is part of Carluke Learning Community who have worked together to develop more effective transition activities and the moderation of writing across all stages This has included a LC working group and LC moderation activities throughout the year resulting in greater confidence for staff. This work will be further developed during session 2025-2026 including the development of consistent marking criteria and resources to support teacher professional judgements of writing levels.

With the Scottish Government’s aim to close the poverty related attainment gap, it is vital to understand and respond to the gaps that inhibit learners reaching their potential.  In accordance with the SIMD there are no pupils in decile 1 and 2 at Law PS. We have 36 pupils entitled to FSM. Our Pupil Equity Funding of £36,750 includes a carry forward of only £0.47 from session 2024-2025.  Our participatory budget is 5% (£1837.50) and will be allocated following consultation with stakeholders in October 2025.

Work to support families has proven that deprivation is more prominent, with a small number of families receiving regular foodbank referrals, Christmas donations and food and clothing parcels which has been supported by funding from the local Scotmid and contributions from the school community.

The ethos and culture of our school is one of our key strengths. We pride ourselves in the positive and friendly ethos that extends to all within the school and local community. We work hard to encourage positive partnerships to uphold our school vision and values and to prove the best educational experience possible for our pupils within a nurturing and safe environment. Our values are positivity, determination, kindness, trust, respect, & responsibility. Our school motto and theme song, #wearelawesome help to inspire and motivate our school community. We actively promote leadership at all levels with teaching staff, support staff, early years practitioners taking leadership in priority improvement areas including Numeracy and Mathematics, Reading Schools, Outdoor Learning, Nurture, and Play-Based Learning. Parent partnerships are key to our success with parental leadership and support successfully running after school clubs, whole school events and fundraisers. Parents have many opportunities to participate in the learner journey through open lessons, showcases, assemblies, performances, and consultations. We also have an active Parent Teacher Association who are engaged and participate in the daily life of the school.

Pupil leadership is a key strength of our school. Opportunities include Rights Respecting School Award group, JRSOs, Young Leaders Of Learning, ECO Team, Reading Schools Champions, Health Ambassadors, & Club Leaders. Our pupils lead a wide range of extra-curricular lunchtime clubs, totalling 16 clubs. This year opportunities included, art club, netball, badminton, & basketball. Our senior pupils also have responsibility for positive play in the playground through our Games Crew initiative which has a positive impact on play with zones around the school grounds including racetrack, construction, sandpit, loose parts, and many more. Our house and vice captains also play a significant role in leading fundraising activities for local and national charities.

We are proud to be an award-winning school having secured our Rights Respecting Schools Award, Reading Schools Award and School for Nature Award. During session 2025-2026 we aim to secure an ECO flag, at least two Digital Schools Awards and start the process of becoming a STEM Nation Award school through the creation of a STEM Lab providing a physical centre for the exploration of STEM knowledge and skills.

During the summer break our nursery will be expanded to increase capacity, this includes extension to the ELC playroom, new storage spaces, new offices and toilets.

OUR SCHOOL VALUES

School values underpin the ethos and culture of our school. Our values are:

POSITIVITY | KINDNESS | TRUST | RESPONSIBILITY | DETERMINATION

OUR SCHOOL RULES

We have high expectations of our pupils’ behaviour and achievements. Our pupils are taught to follow these rules:

READY | RESPECTFUL | SAFE

OUR SCHOOL MOTTO

We aim for excellence in what we do and who we are as a school community and proudly declare:

#wearelawesome

Context of school

Strategic Priority 1: Learning for Sustainability			        Improvement Planning and Standards and Quality Reporting 2025/2026

| NIF Priority (select from drop down menus) Choose an item. NIF Outcome Choose an item. Choose an item. | SLC Priority (select from drop down menus) Choose an item. Choose an item. | SLC Stretch Aims Choose an item. Choose an item. | HGIOS?4 QIs (select from drop down menus) Choose an item. Choose an item. Choose an item. HGIOELC QIs (select from drop down menus) Choose an item. Choose an item. Choose an item. |  |
| --- | --- | --- | --- | --- |
| Rationale for strategic priority | Outcome (Intended impact) | Operational activity | Measures | School Lead |
| LfS weaves together global citizenship, sustainable development and outdoor learning. LfS is an entitlement for all learners within CfE; is embedded within the GTCS Professional Standards; permeates HGIOS and key within GIRFEC. It is at the heart of the Scottish Government’s National Performance Framework to ensure that every school and early learning setting in Scotland will be sustainable by 2030. As a school we aim to ensure our curriculum linked outdoor learning is a regular part of our practice. UNCRC (Incorporation) (Scotland) Act 2024 comes into effect in July. We need to ensure that our school meets the legislation and is working towards a better understanding of all aspects of Rights, Equalities and Sustainability. | As an ongoing priority, we will be confident that all our school community are aware of the UNCRC and children’s rights. Our school will respect and promote the holistic development and wellbeing of every child. By December 2025, all pupils will have participated in global citizenship and sustainability projects. We will achieve one ECO flag. All classes will create a class charter based on children’s rights. Rights will be referenced, displayed and the language of rights used by all. An increase in the confidence, skill and regularity of outdoor learning experiences will be evident across all stages Educating students about the Sustainable Development Goals holds significance as it empowers them to acknowledge their role in shaping the future and encourages collective efforts towards fostering a more sustainable and improved world for all. | GLOBAL CITIZENSHIP - From August 2025, global citizen projects will continue to be implemented across all stages, including Seeds for Change at Early Level, Pants to Poverty and Farm To Fork in First Level, and enterprise projects in Second Level - The Green Team (Eco Committee) have leadership responsibility for achieving Eco-Schools Green Flag accreditation RIGHTS AND SUSTAINABILITY - RRS pupil leadership group will achieve Silver: Rights Aware Award by March/April 2026 - From August 2025, training will be completed by all staff through implementation of updated Making Rights Real framework SUSTAINABLE DEVELOPMENT - ELC and primary classes will participate in LfS from August 2025, with particular focus on sustainable development goals; RHET specific programme, and Keep Scotland Beautiful programme OUTDOOR LEARNING - Teaching and support staff complete second session of training from Learning Through Landscapes including Whole-School Approach course and Playtime Revolution for Support Staff | Survey of learners’ engagement with challenges and opportunities of our world through development of knowledge, skills, values and attitudes using Glasgow Motivation and Wellbeing Profile. By December 2025, our school will achieve one Eco-Schools Green Flag Award through completion of specific goal and topics RRS action plan outcomes and measures detail progress towards achieving Silver Award incl. calendar of events, staff CLPL. Rights will be linked to learning and evident through class visits and self-evaluation. Achievements, class charters, displays, etc will identify the rights of the child and children will be able to speak about their meaning. Surveys by staff and parents will show an increase in understanding and confidence. Evidence gathering: classroom displays, collaborative planning, school assembly presentations, class visits, monitoring of pupil work, self-evaluation discussions with pupils using HGIOURS. Whole staff training increases knowledge and skill in delivering quality outdoor learning. Increased use of outdoor spaces and pupil motivation measured through surveys | All teaching staff ECO lead staff RRS lead staff All teaching staff All teaching and support staff |

| Progress and Impact | Next Step(s) and rationale to inform SIP for 2026/2027 or establishment maintenance agenda |
| --- | --- |
| What difference did we see? What did we achieve? What does your data tell you? Evidence collected to inform self-evaluation. Include bullet points throughout the year on progress of the above. Evaluative statement to be written at end of term as would be in your S&Q. | Clear next steps to be identified based on evidence, and decision if this continues to be a further strategic priority or moves to maintenance. Similar to what has been added to the rationale above. |

Strategic Priority 2: STEM						        Improvement Planning and Standards and Quality Reporting 2025/2026

| NIF Priority (select from drop down menus) Improvement in achievement, particularly in literacy and numeracy. NIF Outcome Inclusive and relevant curriculum and assessment Closing the attainment and achievement gap | SLC Priority (select from drop down menus) Provide a rich and stimulating curriculum that helps raise standards in literacy and numeracy Ensure inclusion, equity and equality are at the heart of what we do | SLC Stretch Aims ACEL Primary – literacy – P1, P4 & P7 combined | HGIOS?4 QIs (select from drop down menus) 1.3 Leadership of change 2.3 Learning, teaching and assessment 3.2 Raising attainment and achievement |  |
| --- | --- | --- | --- | --- |
| Rationale for strategic priority | Outcome (Intended impact) | Operational activity | Measures | School Lead |
| Raising Aspirations in Science Education (RAiSE) empowers primary school practitioners with the confidence, skills, and networks to develop and deliver engaging and motivating STEM learning experiences. The work of the RAiSE programme is aligned to the STEM Education and Training Strategy and the Developing the Young Workforce Programme. It aims to raise attainment and achievement in primary science and STEM, and tackle inequity and inequality in learners’ experiences and outcomes. | As an ongoing priority, all teaching staff will use planning frameworks in science, technology, digital literacy & computing science ensuring consistent approaches to quality learning and teaching All teaching staff will use appropriate instruction to support learners progress within STEM As an ongoing priority, all pupils will experience STEM related challenges and projects and will recognise its importance From August, most pupils will increase knowledge of STEM skills and identified stages track through skills passports | By September 2025, an audit of STEM using Education Scotland STEM self-evaluation and improvement framework will be carried out to evaluate our approaches to STEM. Establish STEM staff and pupil leadership group to lead participation in STEM Nation Award programme. SCIENCE Audit implementation of Science Skills Framework and review effectiveness of skills passports for targeted stages. Science Progression planners implemented by all teaching staff Self-evaluate pupil knowledge, skills and attitudes through Science Skills Passports Available resources audited and new resources identified to support STEM TECHNOLOGIES Develop STEM Lab providing physical space for learning and teaching and development of STEM skills. Identify associated resources and staff CLPL. Technologies planners will be introduced for all levels and resources purchased to support learning and teaching. Teachers attend SLC DO led CLPL through planned INSET ½ Day (10.11.25) to improve digital literacy and computing science learning, teaching and assessment approaches. Establish teacher and pupil leadership group with responsibility for Digital Schools Award – audit using self-evaluation toolkit; create action plan and gather evidence | Completed Ed.Scot. audit using HGIOS indicators and next steps identified and shared with all stakeholders STEM Nation Award provides structure for whole setting strategy for effective STEM learning Identified staff attend training and cascade professional learning to all through CAT / INSET resulting in increased knowledge, skills and confidence. Evidence: forward planning; classroom observations; learner conversations using HGIOURS; collaborative planning; monitoring science skills passports Evidence: forward planning; professional dialogue, feedback from CLPL Digital Schools Award action plan outcomes and measures detail progress towards achieving at least 2 digital awards. | STEM lead teacher All teaching staff STEM lead teacher SLC DO Digital School lead staff |

| Progress and Impact | Next Step(s) and rationale to inform SIP for 2026/2027 or establishment maintenance agenda |
| --- | --- |
| What difference did we see? What did we achieve? What does your data tell you? Evidence collected to inform self-evaluation. Include bullet points throughout the year on progress of the above. Evaluative statement to be written at end of term as would be in your S&Q. | Clear next steps to be identified based on evidence, and decision if this continues to be a further strategic priority or moves to maintenance. Similar to what has been added to the rationale above. |

Strategic Priority 3: LC writing moderation				        Improvement Planning and Standards and Quality Reporting 2025/2026

| NIF Priority (select from drop down menus) Improvement in achievement, particularly in literacy and numeracy. NIF Outcome Inclusive and relevant curriculum and assessment Closing the attainment and achievement gap | SLC Priority (select from drop down menus) Provide a rich and stimulating curriculum that helps raise standards in literacy and numeracy Ensure inclusion, equity and equality are at the heart of what we do | SLC Stretch Aims ACEL Primary – literacy – P1, P4 & P7 combined | HGIOS?4 QIs (select from drop down menus) 1.3 Leadership of change 2.3 Learning, teaching and assessment 3.2 Raising attainment and achievement |  |
| --- | --- | --- | --- | --- |
| Rationale for strategic priority | Outcome (Intended impact) | Operational activity | Measures | School Lead |
| Following shared moderation activity across our Learning Community in 24/25, evidence shows that confidence in making teacher professional judgements in writing has increased. To increase writing attainment, next steps identified the need to review the criteria to inform TPJ in Writing for all learners across Early, First and Second Level, increasing staff understanding of what achievement of a level looks like at each stage. | Provide opportunities for teaching staff to review evidence gathered across a range of abilities in writing. Increase staff confidence that professional judgements are robust, moderated and accurate in almost all cases. Increase staff understanding of what is required to achieve end-of-level milestones (P1/4/7). Increase staff understanding of what is required to achieve mid-level milestones (P2/3/5/6) in writing. Increase opportunities for working across Early Years/Primary and Primary/Secondary to develop understanding of progress across all levels. Increase writing attainment in the LC by at least 1%. | LC working group (established 24/25) will meet at least 6 times across the session. September 2025 – Working group will collate and distribute examples of writing across EY-P7, showcasing achievement of a level. September 2025 – Working group to agree a shared set of criteria to be used throughout moderation tasks. October - November 2025 – All schools to make use of writing criteria/examples of work, as part of in-house moderation activity. February 2026 – LC Inset Day will provide an opportunity for all teachers to take part in moderation of writing activity, using agreed criteria and exemplar folders. May 2026 – analyse writing attainment data across each school and the LC. | Attainment data in Writing – 24/25 and 25/26, across each school and the Learning Community. We would aim for an increase in Writing attainment of at least 1% across the LC. A bank of resources will be distributed to provide support for teachers making professional judgements at each stage of learning (EY – S1). Teacher evaluations will inform next steps for moderation activity. | Hazel Buchanan (DHT, CDPS) Lorna Kilgallon (DHT, Law PS) One lead from each LC Primary School, Nursery and CHS |

| Progress and Impact | Next Step(s) and rationale to inform SIP for 2026/2027 or establishment maintenance agenda |
| --- | --- |
| What difference did we see? What did we achieve? What does your data tell you? Evidence collected to inform self-evaluation. Include bullet points throughout the year on progress of the above. Evaluative statement to be written at end of term as would be in your S&Q. | Clear next steps to be identified based on evidence, and decision if this continues to be a further strategic priority or moves to maintenance. Similar to what has been added to the rationale above. |

Strategic Priority 4: VCPA						        Improvement Planning and Standards and Quality Reporting 2025/2026

| NIF Priority Closing the attainment gap between the most and least disadvantaged children and young people NIF Outcome Globally respected, empowered, responsive education system; leadership, accountability, improvement Staff and SLT driving excellent LTA skills, esp. for learners with ASN | SLC Priority Provide a rich and stimulating curriculum that helps raise standards in literacy and numeracy Support children and young people to develop their skills for learning, life and work | SLC Stretch Aims ACEL Primary – literacy – P1, P4 & P7 combined ACEL Primary – numeracy – P1, P4 & P7 combined | HGIOS?4 Qis 1.3 Leadership of change 2.3 Learning, teaching and assessment 3.3 Increasing creativity and employability HGIOELC QIs 1.3 Leadership of change 2.2 Curriculum 2.3 Learning teaching and assessment |  |
| --- | --- | --- | --- | --- |
| Rationale for strategic priority | Outcome (Intended impact) | Operational activity | Measures | School Lead |
| Numeracy and Mathematics attainment data highlights the need to focus on continuing to improve progress and attainment levels in numeracy and mathematics for learners through high quality learning, teaching and assessment approaches developed through the professional learning materials of the SLC VCPA Professional Learning offer. | By December 2025 almost all teachers will have increased practitioner knowledge, confidence and skills in teaching Numeracy and Mathematics- using the pedagogical approach VCPA. By December 2025, all pupils will have increased access to a wide range of concrete materials during Numeracy and Mathematics learning. By December 2025, majority of pupils will be able to select and use the materials they will need to access Numeracy and Mathematics learning. By February 2026, majority of pupils will be able to explain their choices around selection of materials and/or strategies they use to solve numeracy /mathematical problems. | Teachers attend CLPL through planned INSET ½ Day (12.08.25) and 5 liaison sessions to improve Numeracy and Mathematics learning, teaching and assessment approaches. Teachers complete pre-CLPL questionnaires Audit of VCPA materials and follow up procurement of resources. Teachers engage with a range of VPCA resources on SLC Staff Learning Centre, Curriculum Hub. Staff engage in collaborative activity to support implementation of VCPA approaches. e.g. opportunities to plan/implement/review Staff will gather information about pupils’ understanding and progress in an aspect of numeracy and/or mathematics learning where the learning, teaching and assessment approach is VCPA. Teachers complete post CLPL questionnaires. | Pre and post- CLPL questionnaire for teachers to gauge knowledge, confidence and skills in supporting learners using the VCPA learning, teaching and assessment approach (August 2025 and December 2025/January 2026) VCPA resources overview pre and post audit. Information collated from learning walks during numeracy and maths learning about pupil access to and engagement with VCPA materials. Teacher and pupil focus groups to facilitate direct observation of pupils engaging with VCPA resources and pupil dialogue which supports pupils to explain their choices and strategies. | All teaching staff |

| Progress and Impact | Next Step(s) and rationale to inform SIP for 2026/2027 or establishment maintenance agenda |
| --- | --- |
| What difference did we see? What did we achieve? What does your data tell you? Evidence collected to inform self-evaluation. Include bullet points throughout the year on progress of the above. Evaluative statement to be written at end of term as would be in your S&Q . | Clear next steps to be identified based on evidence, and decision if this continues to be a further strategic priority or moves to maintenance. Similar to what has been added to the rationale above. |

PEF Improvement Planning and Standards and Quality Reporting for 2025/26

Allocation: £36,750.47

| SLC Stretch Aims ACEL Primary – literacy – P1, P4 & P7 combined ACEL Primary – numeracy – P1, P4 & P7 combined Cost of the School Day |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Rationale for PEF / PB Spend | Allocation of PEF / PB spend | Outcome (Intended impact) | Operational activity | Measures | Mid year review RAG | End of year review RAG |
| Analysis of attainment data identified group of 9x P3, 12x P4, 6x P5, 11x P6, 8x P7 pupils for support through targeted reading interventions. | £3,759.00 | Increased attainment level by at least one PiL level, affecting overall attainment by up to 15%. | Targeted interventions including, IDL, Catch-Up Literacy, Literacy Shed, Reading Eggs and summative assessments including NGRT | Interventions assessment data Literacy attainment data Assessment information gathered in writing jotters Tracking and monitoring dialogue |  |  |
| Analysis of attainment data identified group of 8x P6, 9x P7 pupils for support in numeracy. | £5,990.00 | Increased attainment level by up to 10%. By December 2025, majority of pupils will be able to select and use the materials they will need to access Numeracy and Mathematics learning. | Staff CLPL and procurement of additional resources to support VCPA approaches in maths/numeracy | Numeracy attainment data Assessment information gathered in numeracy jotters, MALT assessments, VCPA assessment data, Sumdog data Tracking and monitoring dialogue |  |  |
|  | £8,225.00 | Reduction or removal of costs for all pupils to ensure equitable access to physical education and sporting experiences, enhancing healthy lifestyles and increasing participation levels | Swimming lessons for all P6 pupils at no cost Sports activities at no cost for all pupils Booking coaches through Active Schools for additional sports activities Residential subsidy for all pupils and no cost for targeted individuals Trip subsidies for all pupils and no cost for targeted individuals | Participation and engagement levels monitored |  |  |
|  | £3,800.00 | Increase in positive play experiences at break times Increase opportunities for quality outdoor learning experiences | All teaching staff and support staff will participate in Learning Through Landscapes training to support delivery of high-quality outdoor learning and positive play in the playground Organise nurture breaks to support targeted pupils | Evaluate positive play – reduction in distressed behaviours Evaluate outdoor learning, training through professional dialogue and levels of motivation in pupils |  |  |
|  | £9,420.00 | Increase opportunities for quality STEM learning experiences | Development of STEM Lab to support delivery of high-quality learning and teaching |  |  |  |
|  | £5,500.00 | Reduction or removal of costs associated with transport and travel for all families due to rural location and access to sporting and cultural experiences | Subsidy for all travel and transport costs | Participation and engagement levels monitored |  |  |
|  | TOTAL SPEND (incl carry forward) £36,694.00 |  |  |  |  |  |

| Progress and Impact | Next Step(s) and rationale to inform PEF spend session 2026/2027. |
| --- | --- |

Maintenance Agenda

| Key actions | Relevant stakeholder involvement | Timeline for completion |
| --- | --- | --- |
| Further development of skills-based learning across all stages | All teaching staff | Throughout session |
| Further development of leadership 1.3 Leadership of Change through increased pupil leadership opportunities, staff leadership across ELC & primary, increased involvement of parental leadership through award-based improvements | All | June 2026 |

Evaluation of Quality Indicators

| Quality Indicator | School Self-Evaluation | Nursery Self-Evaluation |
| --- | --- | --- |
| 1.3 Leadership of change | Good | Good |
| 2.3 Learning, teaching and assessment | Good | Good |
| 3.1 Ensuring wellbeing, equality and inclusion | Good | Good |
| 3.2 Raising attainment and achievement Securing children’s progress | Satisfactory | Good |

School:                      Month:		Year: